## FY19 Research Cruise Schedule
Start Date | End Date | Port - Depart | Port - Arrive | DAS | Cruise Location | Personnel | Name: Activities | Project | Ship & Cruise No. | Cruise Plan/Instructions | Cruise Report/Summary | Cruise Statistics | CTD Logs | Land POC | NOAA Teacher at Sea Program | Shipment POC | Shipment Drop-dead Date (for Details see 'Operation Timeline' tab in this document) | Nutrient POC | LAST UPDATE: | 2019-11-21 | 15:12
2019-01-29 | 2019-01-30 | Seattle, WA | Seattle, WA | 0 | Puget Sound | Chief Scientist: TBD; 0 (AFSC) TBD; 0 (PMEL) None; 0 (ABL) | / Gear Trials (OMAO-5410): Equipment: TBD; ITAE Technologies: None; DBO: No | MACE | OMAO-5410 | n/a | n/a | n/a | n/a | J. Napp | None | N/A | 2019-04-05 | TBD
2019-04-19 | 2019-05-02 | Kodiak, AK | Dutch Harbor, AK | 14 | Bering Sea | Chief Scientist: P. Proctor; 2 (AFSC) M. Paquin (FPC), L. Rogers; 4 (PMEL) G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe; 1 (ABL) L. Eisner | Spring Mooring/ FOCI Moorings - Bering Sea (DY19-04): Equipment: Moorings (w/ Prawler), CTD, bongo, CalVet, towfish; ITAE Technologies: Oculus (401 deploy, 40X back-up); DBO: No | NPCREP, EcoFOCI | DY19-04 | no | no | no | no | P. Stabeno | None | G. Lebon | TBD | P. Proctor
2019-05-05 | 2019-05-25 | Dutch Harbor, AK | Kodiak, AK | 21 | Gulf of Alaska | Chief Scientist: A. Doughherty; 4 (AFSC) S. Porter, J. Lamb, C. Harpold; 0 (PMEL) None; 1 (ABL) | WGOA Ichthyoplankton/ EMA-FOCI Larval Groundfish Assessment (DY19-05): Equipment: neuston, bongo, fastcat, CalVET, drifters; ITAE Technologies: None; DBO: No | NPCREP, EcoFOCI, EMA | DY19-05 | yes | yes | no | no | J. Duffy-Anderson | None | G. Lebon | TBD | TBD
2019-05-05 | 2019-06-08 | Seattle, WA | Kodiak, AK | 0 | Gulf of Alaska | Chief Scientist: J. Cross; 0 (AFSC) None; 2 (PMEL) D. Strausz; 0 (ABL) None | GOAOA/ Gulf of Alaska Ocean Acidification (Cancelled): Equipment: CTD, bongo; ITAE Technologies: None; DBO: No | OAP | Cancelled | n/a | n/a | n/a | n/a | J.Cross | N/A | N/A | N/A | N/A
2019-07-31 | 2019-08-24 | Dutch Harbor, AK | Nome, AK | 25 | US Arctic: Chukchi Sea | Chief Scientist: R. McCabe; 1 (AFSC) L. Logerwell (FPC); 3 (PMEL) S. Donohoe, C. Berchock, D. Strausz; 1 (ABL) L. Eisner | Arctic Integrated Ecosystem Survey: MOORINGS Leg 1/ NPRB Arctic IERP (OS19-01 Leg 1): Equipment: acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (401 recover & 404 deploy), Pop-up (4), RAS mooring (1), SM Prawler (TBD); DBO: Yes | NPRB AIERP | OS19-01 Leg 1 | no | no | no | no | E. Farley | None | G. Lebon | TBD | P. Proctor
2019-08-02 | 2019-08-23 | Barrow, AK | Barrow, AK | 22 | US Arctic: Chukchi Sea | Chief Scientist: B. Pickart; 2 (AFSC) J. Duffy-Anderson, Benson, Hayes (Sea Grant); 1 (PMEL) E. Wisegarver ; 0 (ABL) | DBO-NCIS Moorings/ NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) (HL19-00): Equipment: CTD, bongo; ITAE Technologies: TBD; DBO: Yes | EcoFOCI & ITAE | HL19-00 | no | no | no | no | R. Crain | None | G. Lebon | TBD | P. Proctor
2019-08-13 | 2019-08-26 | Kodiak, AK | Kodiak, AK | 14 | Gulf of Alaska | Chief Scientist: M. Wilson; 4 (AFSC) L. Rogers, M. Busby, A. Deary; 1 (PMEL) H. Tabisola; 2 (ABL) W. Strasburger, D. Nicolls, C. Harris (TAS) | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 1): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA, EcoFOCI | DY19-07 Leg 1 | yes | no | no | no | J. Duffy-Anderson | 1 | M. Wilson | TBD | TBD
2019-08-25 | 2019-09-14 | Nome, AK | Nome, AK | 21 | US Arctic: Chukchi Sea | Chief Scientist: E. Farley; TBD (AFSC) L. Logerwel (FPC), D. Cooper, D. Kimmel; 1 (PMEL) S. Donohoe; 4 (ABL) | Arctic Integrated Ecosystem Survey: TRAWLING Leg 2/ NPRB Arctic IERP (OS19-01 Leg 2): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: None; DBO: Yes | NPRB AIERP | OS19-01 Leg 2 | no | no | no | no | E. Farley | None | S. Donohoe/Kris Cieciel | TBD | P. Proctor
2019-08-29 | 2019-09-14 | Kodiak, AK | Dutch Harbor, AK | 17 | Gulf of Alaska | Chief Scientist: S. Porter; 4 (AFSC) A. Dougherty, M. Paquin, C. Harpold; 1 (PMEL) P. Proctor; 3 (ABL) J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS) | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 2): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA, EcoFOCI | DY19-07 Leg 2 | yes | no | no | no | J. Duffy-Anderson | 1 | S. Porter | TBD | TBD
2019-09-13 | 2019-10-02 | Nome, AK | Dutch Harbor, AK | 20 | US Arctic: Chukchi Sea | Chief Scientist: K. Cieciel; 1 (AFSC) D. Cooper (FPC), A. Spear, E. Goldstein; 1 (PMEL) D. Strausz; 4 (ABL) | Arctic Integrated Ecosystem Survey: TRAWLING Leg 3/ NPRB Arctic IERP (OS19-01 Leg 3): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (404 recover), Pop-up (TBD); DBO: Yes | NPRB AIERP | OS19-01 Leg 3 | no | no | no | no | E. Farley | None | D. Strausz | TBD | P. Proctor
2019-09-18 | 2019-10-02 | Dutch Harbor, AK | Kodiak, AK | 15 | Bering Sea | Chief Scientist: P. Proctor; 2 (AFSC) J. Lamb, A. Deary; 7 (PMEL) G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson; 0 (ABL) | Fall Mooring/ FOCI Moorings - Bering Sea (DY19-08): Equipment: Moorings, CTD, bongo, CalVet; ITAE Technologies: Oculus (B recover), Pop-up (TBD); DBO: Yes | EMA, EcoFOCI | DY19-08 | no | no | no | no | P. Stabeno | None | G. Lebon | TBD | P. Proctor
TBD | TBD | Sitka, AK | Juneau, AK | TBD | Gulf of Alaska | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5 (ABL) | EGOA SECM Survey/ Eastern Gulf of Alaska(EGOA) Southeast Alaska Coastal Monitoring (SECM) Survey (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA | XX19-00 |  |  |  |  | TBD | None | TBD | TBD | TBD
TBD | TBD | Dutch Harbor, AK | Dutch Harbor, AK | TBD | US Arctic: Bering Sea | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5-6 (ABL) | EMA/ADFG NBS/ Joint AFSC/ADFG research/ EMA/ADFG NBS/ Joint AFSC/ADFG research (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA | XX19-00 |  |  |  |  | TBD | None | J. Lamb | TBD | TBD
2019-07-12 | 2019-08-01 | Dutch Harbor, AK | Dutch Harbor, AK | 21 | US Arctic: Bering Sea | Chief Scientist: C. Wilson; 0 (AFSC) None; 0 (PMEL) None; 0 (ABL) | Eastern Bering Sea Bottom Trawl Survey Leg 3/ Eastern Bering Sea Bottom Trawl Survey (AK19-01): Equipment: moorings; ITAE Technologies: None; DBO: No | MACE | AK19-01 |  |  |  |  | C. Wilson | None | G. Lebon | TBD | N/A

## FY19_Webpage
Start Date | End Date | Port - Depart | Port - Arrive | DAS | Cruise Location | Personnel | Name: Activities | Project | Ship & Cruise No.
2019-01-29 | 2019-01-30 | Seattle, WA | Seattle, WA | 0 | Puget Sound | Chief Scientist: TBD; 0 (AFSC) TBD; 0 (PMEL) None; 0 (ABL) | / Gear Trials (OMAO-5410): Equipment: TBD; ITAE Technologies: None; DBO: No | MACE | OMAO-5410
2019-04-19 | 2019-05-02 | Kodiak, AK | Dutch Harbor, AK | 14 | Bering Sea | Chief Scientist: P. Proctor; 2 (AFSC) M. Paquin (FPC), L. Rogers; 4 (PMEL) G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe; 1 (ABL) L. Eisner | Spring Mooring/ FOCI Moorings - Bering Sea (DY19-04): Equipment: Moorings (w/ Prawler), CTD, bongo, CalVet, towfish; ITAE Technologies: Oculus (401 deploy, 40X back-up); DBO: No | NPCREP, EcoFOCI | DY19-04
2019-05-05 | 2019-05-25 | Dutch Harbor, AK | Kodiak, AK | 21 | Gulf of Alaska | Chief Scientist: A. Doughherty; 4 (AFSC) S. Porter, J. Lamb, C. Harpold; 0 (PMEL) None; 1 (ABL) | WGOA Ichthyoplankton/ EMA-FOCI Larval Groundfish Assessment (DY19-05): Equipment: neuston, bongo, fastcat, CalVET, drifters; ITAE Technologies: None; DBO: No | NPCREP, EcoFOCI, EMA | DY19-05
2019-05-05 | 2019-06-08 | Seattle, WA | Kodiak, AK | 0 | Gulf of Alaska | Chief Scientist: J. Cross; 0 (AFSC) None; 2 (PMEL) D. Strausz; 0 (ABL) None | GOAOA/ Gulf of Alaska Ocean Acidification (Cancelled): Equipment: CTD, bongo; ITAE Technologies: None; DBO: No | OAP | Cancelled
2019-07-31 | 2019-08-24 | Dutch Harbor, AK | Nome, AK | 25 | US Arctic: Chukchi Sea | Chief Scientist: R. McCabe; 1 (AFSC) L. Logerwell (FPC); 3 (PMEL) S. Donohoe, C. Berchock, D. Strausz; 1 (ABL) L. Eisner | Arctic Integrated Ecosystem Survey: MOORINGS Leg 1/ NPRB Arctic IERP (OS19-01 Leg 1): Equipment: acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (401 recover & 404 deploy), Pop-up (4), RAS mooring (1), SM Prawler (TBD); DBO: Yes | NPRB AIERP | OS19-01 Leg 1
2019-08-02 | 2019-08-23 | Barrow, AK | Barrow, AK | 22 | US Arctic: Chukchi Sea | Chief Scientist: B. Pickart; 2 (AFSC) J. Duffy-Anderson, Benson, Hayes (Sea Grant); 1 (PMEL) E. Wisegarver ; 0 (ABL) | DBO-NCIS Moorings/ NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) (HL19-00): Equipment: CTD, bongo; ITAE Technologies: TBD; DBO: Yes | EcoFOCI & ITAE | HL19-00
2019-08-13 | 2019-08-26 | Kodiak, AK | Kodiak, AK | 14 | Gulf of Alaska | Chief Scientist: M. Wilson; 4 (AFSC) L. Rogers, M. Busby, A. Deary; 1 (PMEL) H. Tabisola; 2 (ABL) W. Strasburger, D. Nicolls, C. Harris (TAS) | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 1): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA, EcoFOCI | DY19-07 Leg 1
2019-08-25 | 2019-09-14 | Nome, AK | Nome, AK | 21 | US Arctic: Chukchi Sea | Chief Scientist: E. Farley; TBD (AFSC) L. Logerwel (FPC), D. Cooper, D. Kimmel; 1 (PMEL) S. Donohoe; 4 (ABL) | Arctic Integrated Ecosystem Survey: TRAWLING Leg 2/ NPRB Arctic IERP (OS19-01 Leg 2): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: None; DBO: Yes | NPRB AIERP | OS19-01 Leg 2
2019-08-29 | 2019-09-14 | Kodiak, AK | Dutch Harbor, AK | 17 | Gulf of Alaska | Chief Scientist: S. Porter; 4 (AFSC) A. Dougherty, M. Paquin, C. Harpold; 1 (PMEL) P. Proctor; 3 (ABL) J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS) | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 2): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA, EcoFOCI | DY19-07 Leg 2
2019-09-13 | 2019-10-02 | Nome, AK | Dutch Harbor, AK | 20 | US Arctic: Chukchi Sea | Chief Scientist: K. Cieciel; 1 (AFSC) D. Cooper (FPC), A. Spear, E. Goldstein; 1 (PMEL) D. Strausz; 4 (ABL) | Arctic Integrated Ecosystem Survey: TRAWLING Leg 3/ NPRB Arctic IERP (OS19-01 Leg 3): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (404 recover), Pop-up (TBD); DBO: Yes | NPRB AIERP | OS19-01 Leg 3
2019-09-18 | 2019-10-02 | Dutch Harbor, AK | Kodiak, AK | 15 | Bering Sea | Chief Scientist: P. Proctor; 2 (AFSC) J. Lamb, A. Deary; 7 (PMEL) G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson; 0 (ABL) | Fall Mooring/ FOCI Moorings - Bering Sea (DY19-08): Equipment: Moorings, CTD, bongo, CalVet; ITAE Technologies: Oculus (B recover), Pop-up (TBD); DBO: Yes | EMA, EcoFOCI | DY19-08
TBD | TBD | Sitka, AK | Juneau, AK | TBD | Gulf of Alaska | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5 (ABL) | EGOA SECM Survey/ Eastern Gulf of Alaska(EGOA) Southeast Alaska Coastal Monitoring (SECM) Survey (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA | XX19-00
TBD | TBD | Dutch Harbor, AK | Dutch Harbor, AK | TBD | US Arctic: Bering Sea | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5-6 (ABL) | EMA/ADFG NBS/ Joint AFSC/ADFG research/ EMA/ADFG NBS/ Joint AFSC/ADFG research (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA | XX19-00
2019-07-12 | 2019-08-01 | Dutch Harbor, AK | Dutch Harbor, AK | 21 | US Arctic: Bering Sea | Chief Scientist: C. Wilson; 0 (AFSC) None; 0 (PMEL) None; 0 (ABL) | Eastern Bering Sea Bottom Trawl Survey Leg 3/ Eastern Bering Sea Bottom Trawl Survey (AK19-01): Equipment: moorings; ITAE Technologies: None; DBO: No | MACE | AK19-01

## SHIPPING LOGISTICS & TIMELINE
Cruise No. | Vessel | Cruise Dates | Depart Port | Arrive Port | Drop-dead Date | Shipment Details/Notes | Vehicles deployed | FOCI/ITAE Moorings Deployed | FOCI/ITAE Moorings Recovered | MML Moorings Deployed | MML Moorings Recovered | Pop-ups Deployed | Shipment POC | Hazmats
OMAO-5410 | NOAAS Oscar Dyson |  | Seattle, WA | Seattle, WA | N/A |  | None | None |  | None |  | None | N/A | N
DY19-04 | NOAAS Oscar Dyson | 04/19/19 - 05/02/19 | Kodiak, AK | Dutch Harbor, AK | 2019-04-08 | Load at pier 91 on the 10th of April... Return Shipment June 2nd from Kodiak by barge following DY19-03 **Return shipment actually arriving July 11th** | Oculus (401 deploy, 40X back-up) | 19CB1A, 19BSM2A, 19BSP2A, 19BSITAEPR-2A (PRAWLER) |  | MML, AL19_AU_BS4, AL19_AU_BS6, AL19_AU_BS3 |  | None | G. Lebon | Y | Done
DY19-05 | NOAAS Oscar Dyson | 05/05/19 - 05/25/19 | Dutch Harbor, AK | Kodiak, AK |  | N/A | None | None |  | None |  | None | G. Lebon | N/A
CANCELLED | R/V Ocean Starr | 05/05/19 - 06/08/19 | Seattle, WA | Kodiak, AK | TBD | N/A | N/A | N/A |  | N/A |  | N/A | J.Cross | N/A
OS19-01 Leg 1 | R/V Ocean Starr | 07/31/19 - 08/24/19 | Dutch Harbor, AK | Nome, AK | TBD | Load at Stabbert. Anchors and heavies load via flat rack on 19 July. Gear trials July 20 and 21. Load remaining gear July 22. |  | 19CKIP1A, 19CKP1A, 19CKIP2A, 19CKP2A, 19CKIP3A, 19CKP3A, 19CKP4A, 19CKP5A, 19CKP12A, 19CKR2A, 19CKITAEPR2A (ICE PRAWLER) |  | MML, AL19_AU_NM1, AL19_AU_BF2, AL19_AU_PH1, AL19_AU_CL1, AL19_AU_IC1, AL19_AU_IC2, AL19_AU_IC3, AL19_AU_PB1, AL19_AU_WT1 |  | None | G. Lebon | Y
HL19-00 | USCGC Healy | 08/02/19 - 08/23/19 | Barrow, AK | Barrow, AK |  | N/A | None | None |  | None |  | None | G. Lebon | N/A
DY19-07 Leg 1 | NOAAS Oscar Dyson | 08/13/19 - 08/26/19 | Kodiak, AK | Kodiak, AK | TBD | Load Fisheries Doors, and other equipment | None | None |  | None |  | None | M. Wilson | N
OS19-01 Leg 2 | R/V Ocean Starr | 08/25/19 - 09/14/19 | Nome, AK | Nome, AK | TBD | Container to Nome, loads at bldg 32 on the 26th of June | None | None |  | Some in the above column will go out on this cruise |  | None | S. Donohoe/Kris Cieciel | N/A
DY19-07 Leg 2 | NOAAS Oscar Dyson | 08/29/19 - 09/14/19 | Kodiak, AK | Dutch Harbor, AK | TBD | N/A | None | None |  | None |  | None | S. Porter | Y
OS19-01 Leg 3 | R/V Ocean Starr | 09/13/19 - 10/02/19 | Nome, AK | Dutch Harbor, AK | TBD | Return ship all equipment on the Ocean Starr |  | None |  | MML, AL19_AU_BS2 |  | Popups: [No. 2] 211, 215 | D. Strausz | N
DY19-08 | NOAAS Oscar Dyson | 09/18/19 - 10/02/19 | Dutch Harbor, AK | Kodiak, AK | TBD | Load containers Aug 27th and 28th; Return Shipment on Dyson to lower 48 |  | 19BS2C, 19BSP2B, 19BS4B, 19BSP4A, 19BS5A, 19BSP5A, 19BS8A, 19BSP8A, 19SHP-1A |  | MML, AL19_AU_BS1, AL19_AU_BS9 |  | Popups: [No. 4] 218, 216, 213, 214 | G. Lebon | Y
XX19-00 | CHARTER TBD | TBD - TBD | Sitka, AK | Juneau, AK |  |  | None | None |  | None |  | None | TBD | N/A
XX19-00 | CHARTER TBD | TBD - TBD | Dutch Harbor, AK | Dutch Harbor, AK |  |  |  | None |  | None |  | None | J. Lamb | N/A
AK19-01 | F/V Alaska Knight | 07/12/19 - 08/01/19 | Dutch Harbor, AK | Dutch Harbor, AK | TBD | 2019-06-12 | None | 75 kHz ADCP, 2 - 300 kHz ADCP, 19BSP-10A, 19BSP-11A, 19BSP-12A |  | None |  | None | G. Lebon | N/A | Done

## FY19 Planning
Research Cruise Title | Alternative Research Cruise Title | Vessel | Cruise No. | Cruise Info | Start Date | End Date | Days at Sea | Depart Port | Arrive Port | Line Office | Research Programs | Research Description | EcoFOCI Equipment | ITAE Technologies | Vehicles Deployed | DBO | Activities: Contencate | Land POC | No. of EcoFOCI Personnel (AFSC/SEA) | No. of of EcoFOCI Personnel (PMEL) | No. of RPA Personnel (ABL) | No. of Other Personnel | NOAA Teacher at Sea Program | Total Personnel | Chief Scientist | AFSC Personnel | PMEL Personnel | ABL Personnel | Concatenate | Shipment POC | Shipment Details | Nutrient Samples POC
Gear Trials |  | NOAAS Oscar Dyson | OMAO-5410 | Puget Sound | 2019-01-29 | 2019-01-30 | 0 | Seattle, WA | Seattle, WA | OMAO | MACE | Gear Trials | TBD | None | None | No | / Gear Trials (OMAO-5410): Equipment: TBD; ITAE Technologies: None; DBO: No | J. Napp | 0 | 0 | 0 | 0 | None | 0 | TBD | TBD | None |  | Chief Scientist: TBD; 0 (AFSC) TBD; 0 (PMEL) None; 0 (ABL) | N/A | TBD | TBD
FOCI Moorings - Bering Sea | Spring Mooring | NOAAS Oscar Dyson | DY19-04 | Bering Sea | 2019-04-19 | 2019-05-02 | 14 | Kodiak, AK | Dutch Harbor, AK | OAR | NPCREP, EcoFOCI | 70m isobath, Moorings: M2, M2 Prawler, M4, M5 & St. Matt. Prawler, CB1A turnaround, Deploy St. Matt's Oculus 401 | Moorings (w/ Prawler), CTD, bongo, CalVet, towfish | Oculus (401 deploy, 40X back-up) | Oculus (401 deploy, 40X back-up) | No | Spring Mooring/ FOCI Moorings - Bering Sea (DY19-04): Equipment: Moorings (w/ Prawler), CTD, bongo, CalVet, towfish; ITAE Technologies: Oculus (401 deploy, 40X back-up); DBO: No | P. Stabeno | 2 | 4 | 1 | 0 | None | 0 | P. Proctor | M. Paquin (FPC), L. Rogers | G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe | L. Eisner | Chief Scientist: P. Proctor; 2 (AFSC) M. Paquin (FPC), L. Rogers; 4 (PMEL) G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe; 1 (ABL) L. Eisner | G. Lebon | TBD | P. Proctor
EMA-FOCI Larval Groundfish Assessment | WGOA Ichthyoplankton | NOAAS Oscar Dyson | DY19-05 | Gulf of Alaska | 2019-05-05 | 2019-05-25 | 21 | Dutch Harbor, AK | Kodiak, AK | NMFS | NPCREP, EcoFOCI, EMA |  | neuston, bongo, fastcat, CalVET, drifters | None | None | No | WGOA Ichthyoplankton/ EMA-FOCI Larval Groundfish Assessment (DY19-05): Equipment: neuston, bongo, fastcat, CalVET, drifters; ITAE Technologies: None; DBO: No | J. Duffy-Anderson | 4 | 0 | 1 | 1 | None | 0 | A. Doughherty | S. Porter, J. Lamb, C. Harpold | None |  | Chief Scientist: A. Doughherty; 4 (AFSC) S. Porter, J. Lamb, C. Harpold; 0 (PMEL) None; 1 (ABL) | G. Lebon | TBD | TBD
Gulf of Alaska Ocean Acidification | GOAOA | R/V Ocean Starr | Cancelled | Gulf of Alaska | 2019-05-05 | 2019-06-08 | 0 | Seattle, WA | Kodiak, AK | OAR | OAP | Coastal ocean acidification program, follow-on of 2015, continuous CTD sampling | CTD, bongo | None | None | No | GOAOA/ Gulf of Alaska Ocean Acidification (Cancelled): Equipment: CTD, bongo; ITAE Technologies: None; DBO: No | J.Cross | 0 | 2 | 0 | 0 | None | 0 | J. Cross | None | D. Strausz | None | Chief Scientist: J. Cross; 0 (AFSC) None; 2 (PMEL) D. Strausz; 0 (ABL) None | J.Cross | 2019-05-01 | P. Proctor
NPRB Arctic IERP | Arctic Integrated Ecosystem Survey: MOORINGS Leg 1 | R/V Ocean Starr | OS19-01 Leg 1 | US Arctic: Chukchi Sea | 2019-07-31 | 2019-08-24 | 25 | Dutch Harbor, AK | Nome, AK | OAR | NPRB AIERP | Oculus: recover 401, deploy B & 404, (B-Saint Matthew & 404-Hannah Shoal/Point hope?), C2 Prawler (TBD), Pop-up (4), Alkalinity Mooring?, RAS mooring, Saildrone rendevous (SM Prawler TBD) | acoustics, CTD, bongo, towfish, moorings | Oculus (401 recover & 404 deploy), Pop-up (4), RAS mooring (1), SM Prawler (TBD) |  | Yes | Arctic Integrated Ecosystem Survey: MOORINGS Leg 1/ NPRB Arctic IERP (OS19-01 Leg 1): Equipment: acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (401 recover & 404 deploy), Pop-up (4), RAS mooring (1), SM Prawler (TBD); DBO: Yes | E. Farley | 1 | 3 | 1 | 0 | None | 0 | R. McCabe | L. Logerwell (FPC) | S. Donohoe, C. Berchock, D. Strausz | L. Eisner | Chief Scientist: R. McCabe; 1 (AFSC) L. Logerwell (FPC); 3 (PMEL) S. Donohoe, C. Berchock, D. Strausz; 1 (ABL) L. Eisner | G. Lebon | TBD | P. Proctor
NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) | DBO-NCIS Moorings | USCGC Healy | HL19-00 | US Arctic: Chukchi Sea | 2019-08-02 | 2019-08-23 | 22 | Barrow, AK | Barrow, AK | OAR | EcoFOCI & ITAE |  | CTD, bongo | TBD | None | Yes | DBO-NCIS Moorings/ NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) (HL19-00): Equipment: CTD, bongo; ITAE Technologies: TBD; DBO: Yes | R. Crain | 2 | 1 | 0 | 0 | None | 0 | B. Pickart | J. Duffy-Anderson, Benson, Hayes (Sea Grant) | E. Wisegarver |  | Chief Scientist: B. Pickart; 2 (AFSC) J. Duffy-Anderson, Benson, Hayes (Sea Grant); 1 (PMEL) E. Wisegarver ; 0 (ABL) | G. Lebon | TBD | P. Proctor
EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes | YOY Pollock | NOAAS Oscar Dyson | DY19-07 Leg 1 | Gulf of Alaska | 2019-08-13 | 2019-08-26 | 14 | Kodiak, AK | Kodiak, AK | NMFS | EMA, EcoFOCI |  | midwater trawl, CTD, bongo | None | None | No | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 1): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | J. Duffy-Anderson | 4 | 1 | 2 | 0 | 1 | 0 | M. Wilson | L. Rogers, M. Busby, A. Deary | H. Tabisola | W. Strasburger, D. Nicolls, C. Harris (TAS) | Chief Scientist: M. Wilson; 4 (AFSC) L. Rogers, M. Busby, A. Deary; 1 (PMEL) H. Tabisola; 2 (ABL) W. Strasburger, D. Nicolls, C. Harris (TAS) | M. Wilson | TBD | TBD
NPRB Arctic IERP | Arctic Integrated Ecosystem Survey: TRAWLING Leg 2 | R/V Ocean Starr | OS19-01 Leg 2 | US Arctic: Chukchi Sea | 2019-08-25 | 2019-09-14 | 21 | Nome, AK | Nome, AK | OAR | NPRB AIERP |  | surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings | None | None | Yes | Arctic Integrated Ecosystem Survey: TRAWLING Leg 2/ NPRB Arctic IERP (OS19-01 Leg 2): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: None; DBO: Yes | E. Farley | TBD | 1 | 4 | 0 | None | 0 | E. Farley | L. Logerwel (FPC), D. Cooper, D. Kimmel | S. Donohoe |  | Chief Scientist: E. Farley; TBD (AFSC) L. Logerwel (FPC), D. Cooper, D. Kimmel; 1 (PMEL) S. Donohoe; 4 (ABL) | S. Donohoe/Kris Cieciel | TBD | P. Proctor
EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes | YOY Pollock | NOAAS Oscar Dyson | DY19-07 Leg 2 | Gulf of Alaska | 2019-08-29 | 2019-09-14 | 17 | Kodiak, AK | Dutch Harbor, AK | NMFS | EMA, EcoFOCI |  | midwater trawl, CTD, bongo | None | None | No | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 2): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | J. Duffy-Anderson | 4 | 1 | 3 | 0 | 1 | 0 | S. Porter | A. Dougherty, M. Paquin, C. Harpold | P. Proctor | J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS) | Chief Scientist: S. Porter; 4 (AFSC) A. Dougherty, M. Paquin, C. Harpold; 1 (PMEL) P. Proctor; 3 (ABL) J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS) | S. Porter | TBD | TBD
NPRB Arctic IERP | Arctic Integrated Ecosystem Survey: TRAWLING Leg 3 | R/V Ocean Starr | OS19-01 Leg 3 | US Arctic: Chukchi Sea | 2019-09-13 | 2019-10-02 | 20 | Nome, AK | Dutch Harbor, AK | OAR | NPRB AIERP | Oculus: recover Hannah Shoal/Point Hope Oculus 404, Pop-up Grid Drop (TBD) | surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings | Oculus (404 recover), Pop-up (TBD) |  | Yes | Arctic Integrated Ecosystem Survey: TRAWLING Leg 3/ NPRB Arctic IERP (OS19-01 Leg 3): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (404 recover), Pop-up (TBD); DBO: Yes | E. Farley | 1 | 1 | 4 | 0 | None | 0 | K. Cieciel | D. Cooper (FPC), A. Spear, E. Goldstein | D. Strausz |  | Chief Scientist: K. Cieciel; 1 (AFSC) D. Cooper (FPC), A. Spear, E. Goldstein; 1 (PMEL) D. Strausz; 4 (ABL) | D. Strausz | TBD | P. Proctor
FOCI Moorings - Bering Sea | Fall Mooring | NOAAS Oscar Dyson | DY19-08 | Bering Sea | 2019-09-18 | 2019-10-02 | 15 | Dutch Harbor, AK | Kodiak, AK | OAR, NMFS | EMA, EcoFOCI | 70m isobath, Moorings: M2, M2 Prawler, M4, M5, St. Matt. Prawler, & M8, CB1A turnaround, recover St. Matt's Oculus B, Pop-up Grid Drop (TBD) | Moorings, CTD, bongo, CalVet | Oculus (B recover), Pop-up (TBD) |  | Yes | Fall Mooring/ FOCI Moorings - Bering Sea (DY19-08): Equipment: Moorings, CTD, bongo, CalVet; ITAE Technologies: Oculus (B recover), Pop-up (TBD); DBO: Yes | P. Stabeno | 2 | 7 | 0 | 0 | None | 0 | P. Proctor | J. Lamb, A. Deary | G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson |  | Chief Scientist: P. Proctor; 2 (AFSC) J. Lamb, A. Deary; 7 (PMEL) G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson; 0 (ABL) | G. Lebon | TBD | P. Proctor
Eastern Gulf of Alaska(EGOA) Southeast Alaska Coastal Monitoring (SECM) Survey | EGOA SECM Survey | CHARTER TBD | XX19-00 | Gulf of Alaska | TBD | TBD | TBD | Sitka, AK | Juneau, AK | NMFS | EMA |  | surface trawl, CTD, bongo | None | None | No | EGOA SECM Survey/ Eastern Gulf of Alaska(EGOA) Southeast Alaska Coastal Monitoring (SECM) Survey (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | TBD | 0 | 0 | 5 | 0 | None | 0 | TBD | None | None |  | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5 (ABL) | TBD | TBD | TBD
EMA/ADFG NBS/ Joint AFSC/ADFG research | EMA/ADFG NBS/ Joint AFSC/ADFG research | CHARTER TBD | XX19-00 | US Arctic: Bering Sea | TBD | TBD | TBD | Dutch Harbor, AK | Dutch Harbor, AK | NMFS | EMA |  | surface trawl, CTD, bongo | None | None | No | EMA/ADFG NBS/ Joint AFSC/ADFG research/ EMA/ADFG NBS/ Joint AFSC/ADFG research (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | TBD | 0 | 0 | 5-6 | 0 | None | 0 | TBD | None | None |  | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5-6 (ABL) | J. Lamb | TBD | TBD
Eastern Bering Sea Bottom Trawl Survey | Eastern Bering Sea Bottom Trawl Survey Leg 3 | F/V Alaska Knight | AK19-01 | US Arctic: Bering Sea | 2019-07-12 | 2019-08-01 | 21 | Dutch Harbor, AK | Dutch Harbor, AK | NMFS | MACE | 75 kHz ADCP, 300 kHz ADCP | moorings | None | None | No | Eastern Bering Sea Bottom Trawl Survey Leg 3/ Eastern Bering Sea Bottom Trawl Survey (AK19-01): Equipment: moorings; ITAE Technologies: None; DBO: No | C. Wilson | 0 | 0 | 0 | 0 | None | 0 | C. Wilson | None | None |  | Chief Scientist: C. Wilson; 0 (AFSC) None; 0 (PMEL) None; 0 (ABL) | G. Lebon | TBD | N/A
[29 empty] | Chief Scientist: P. Proctor; 2 (AFSC) M. Paquin (FPC), L. Rogers; 4 (PMEL) G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe; 1 (ABL) L. EisnerChief Scientist: A. Doughherty; 4 (AFSC) S. Porter, J. Lamb, C. Harpold; 0 (PMEL) None; 1 (ABL) Chief Scientist: R. McCabe; 1 (AFSC) L. Logerwell (FPC); 3 (PMEL) S. Donohoe, C. Berchock, D. Strausz; 1 (ABL) L. EisnerChief Scientist: B. Pickart; 2 (AFSC) J. Duffy-Anderson, Benson, Hayes (Sea Grant); 1 (PMEL) E. Wisegarver ; 0 (ABL) Chief Scientist: M. Wilson; 4 (AFSC) L. Rogers, M. Busby, A. Deary; 1 (PMEL) H. Tabisola; 2 (ABL) W. Strasburger, D. Nicolls, C. Harris (TAS)Chief Scientist: E. Farley; TBD (AFSC) L. Logerwel (FPC), D. Cooper, D. Kimmel; 1 (PMEL) S. Donohoe; 4 (ABL) Chief Scientist: S. Porter; 4 (AFSC) A. Dougherty, M. Paquin, C. Harpold; 1 (PMEL) P. Proctor; 3 (ABL) J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS)Chief Scientist: K. Cieciel; 1 (AFSC) D. Cooper (FPC), A. Spear, E. Goldstein; 1 (PMEL) D. Strausz; 4 (ABL) Chief Scientist: P. Proctor; 2 (AFSC) J. Lamb, A. Deary; 7 (PMEL) G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson; 0 (ABL) | Chief Scientist: P. Proctor; 2 (AFSC) M. Paquin (FPC), L. Rogers; 4 (PMEL) G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe; 1 (ABL) L. EisnerChief Scientist: A. Doughherty; 4 (AFSC) S. Porter, J. Lamb, C. Harpold; 0 (PMEL) None; 1 (ABL) Chief Scientist: R. McCabe; 1 (AFSC) L. Logerwell (FPC); 3 (PMEL) S. Donohoe, C. Berchock, D. Strausz; 1 (ABL) L. EisnerChief Scientist: B. Pickart; 2 (AFSC) J. Duffy-Anderson, Benson, Hayes (Sea Grant); 1 (PMEL) E. Wisegarver ; 0 (ABL) Chief Scientist: M. Wilson; 4 (AFSC) L. Rogers, M. Busby, A. Deary; 1 (PMEL) H. Tabisola; 2 (ABL) W. Strasburger, D. Nicolls, C. Harris (TAS)Chief Scientist: E. Farley; TBD (AFSC) L. Logerwel (FPC), D. Cooper, D. Kimmel; 1 (PMEL) S. Donohoe; 4 (ABL) Chief Scientist: S. Porter; 4 (AFSC) A. Dougherty, M. Paquin, C. Harpold; 1 (PMEL) P. Proctor; 3 (ABL) J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS)Chief Scientist: K. Cieciel; 1 (AFSC) D. Cooper (FPC), A. Spear, E. Goldstein; 1 (PMEL) D. Strausz; 4 (ABL) Chief Scientist: P. Proctor; 2 (AFSC) J. Lamb, A. Deary; 7 (PMEL) G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson; 0 (ABL)

## FY19 Summary of Operations
Cruise No. | Research Cruise Title | Chief Scientist | Days at Sea | Research Programs | DBO | No. of EcoFOCI Personnel (AFSC/SEA) | No. of of EcoFOCI Personnel (PMEL) | No. of RPA Personnel (ABL) | No. of Other Personnel | NOAA Teacher at Sea Program | Operations: Bongo Tows | Operations: PMEL Moorings Deployed | Operations: PMEL Mooring Recovered | Operations: Other Moorings deployed/ recovered | Operations: CTD (CTD & CTDB) | RZA
OMAO-5410 | Gear Trials | TBD | 0 | MACE | No | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0
DY19-04 | FOCI Moorings - Bering Sea | P. Proctor | 14 | NPCREP, EcoFOCI | No | 2 | 4 | 1 | 0 | None
DY19-05 | EMA-FOCI Larval Groundfish Assessment | A. Doughherty | 21 | NPCREP, EcoFOCI, EMA | No | 4 | 0 | 1 | 1 | None | 232 | 0 | 0 | 0 | 25 | 124
Cancelled | Gulf of Alaska Ocean Acidification | J. Cross | 0 | OAP | No | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0 | 0
OS19-01 Leg 1 | NPRB Arctic IERP | R. McCabe | 25 | NPRB AIERP | Yes | 1 | 3 | 1 | 0 | None
HL19-00 | NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) | B. Pickart | 22 | EcoFOCI & ITAE | Yes | 2 | 1 | 0 | 0 | None
DY19-07 Leg 1 | EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes | M. Wilson | 14 | EMA, EcoFOCI | No | 4 | 1 | 2 | 0 | 1 | 125 | 0 | 0 | 0 | 19 | 118
OS19-01 Leg 2 | NPRB Arctic IERP | E. Farley | 21 | NPRB AIERP | Yes | TBD | 1 | 4 | 0 | None
DY19-07 Leg 2 | EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes | S. Porter | 17 | EMA, EcoFOCI | No | 4 | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
OS19-01 Leg 3 | NPRB Arctic IERP | K. Cieciel | 20 | NPRB AIERP | Yes | 1 | 1 | 4 | 0 | None
DY19-08 | FOCI Moorings - Bering Sea | P. Proctor | 15 | EMA, EcoFOCI | Yes | 2 | 7 | 0 | 0 | None
XX19-00 |  | TBD | 0 | EMA | No | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0 | 0
XX19-00 |  | TBD | 0 | EMA | No | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0 | 0
AK19-01 |  | C. Wilson | 0 | MACE | No | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0 | 0

## Sheet8
DAS | Cruise Location | Name: Activities | Project | Project
2 | Puget Sound | / Gear Trials (OMAO-5410): Equipment: TBD; ITAE Technologies: None; DBO: No | n/a | MACE
14 | Bering Sea | Spring Mooring/ FOCI Moorings - Bering Sea (DY19-04): Equipment: Moorings (w/ Prawler), CTD, bongo, CalVet, towfish; ITAE Technologies: Oculus (401 deploy, 40X back-up); DBO: No | EcoFOCI | NPCREP, EcoFOCI | EcoFOCI | 169
21 | Gulf of Alaska | WGOA Ichthyoplankton/ EMA-FOCI Larval Groundfish Assessment (DY19-05): Equipment: neuston, bongo, fastcat, CalVET, drifters; ITAE Technologies: None; DBO: No | EcoFOCI | NPCREP, EcoFOCI, EMA
35 | Gulf of Alaska | GOAOA/ Gulf of Alaska Ocean Acidification (Cancelled): Equipment: CTD, bongo; ITAE Technologies: None; DBO: No | OAP | OAP
25 | US Arctic: Chukchi Sea | Arctic Integrated Ecosystem Survey: MOORINGS Leg 1/ NPRB Arctic IERP (OS19-01): Equipment: acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (401 recover & 404 deploy), Pop-up (4), RAS mooring (1), SM Prawler (TBD); DBO: Yes | EcoFOCI | NPRB AIERP
22 | US Arctic: Chukchi Sea | DBO-NCIS Moorings/ NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) (HL19-00): Equipment: CTD, bongo; ITAE Technologies: TBD; DBO: Yes | EcoFOCI | EcoFOCI & ITAE
14 | Gulf of Alaska | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 1): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EcoFOCI | EMA, EcoFOCI
21 | US Arctic: Chukchi Sea | Arctic Integrated Ecosystem Survey: TRAWLING Leg 2/ NPRB Arctic IERP (OS-19-02): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: None; DBO: Yes | EcoFOCI | NPRB AIERP
17 | Gulf of Alaska | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 2): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EcoFOCI | EMA, EcoFOCI
20 | US Arctic: Chukchi Sea | Arctic Integrated Ecosystem Survey: TRAWLING Leg 3/ NPRB Arctic IERP (OS19-03): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (404 recover), Pop-up (TBD); DBO: Yes | EcoFOCI | NPRB AIERP
15 | Bering Sea | Fall Mooring/ FOCI Moorings - Bering Sea (DY19-08): Equipment: Moorings, CTD, bongo, CalVet; ITAE Technologies: Oculus (B recover), Pop-up (TBD); DBO: Yes | EcoFOCI | EMA, EcoFOCI
| Gulf of Alaska | EGOA SECM Survey/ Eastern Gulf of Alaska(EGOA) Southeast Alaska Coastal Monitoring (SECM) Survey (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | n/a | EMA
| US Arctic: Bering Sea | EMA/ADFG NBS/ Joint AFSC/ADFG research/ EMA/ADFG NBS/ Joint AFSC/ADFG research (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | n/a | EMA
21 | US Arctic: Bering Sea | Eastern Bering Sea Bottom Trawl Survey Leg 3/ Eastern Bering Sea Bottom Trawl Survey (AK19-01): Equipment: moorings; ITAE Technologies: None; DBO: No | n/a | MACE

## OPERATION TIMELINE B (hidden)
Cruise No. | Ship | Cruise Dates | Port of Dep/Arriv | Drop-dead Date | Shipment Details | Moorings Deployed | Vehicles deployed | FOCI Lead | Hazmats
DY19-04 | Oscar Dyson | 4/19-5/02 | Kodiak/Dutch | 2019-04-05 | Load at pier 91, 8th and 9th of April | 19CB1A, 19BSM2A, 19BSP2A, 19BSITAEPR-2A | 401 Oculus deployed | Lebon/Grassia | Y
MML, AL19_AU_BS4, AL19_AU_BS6, AL19_AU_BS3
|  |  |  | 2019-06-02 | Return Shipment June 2nd from Kodiak by barge following DY19-03 |  |  |  | Y
OS19-01 | Ocean Starr | 8/01-8/24 | Dutch/Nome |  | Load Seattle, early July, at Stabbert Maritime dock | 19CKIP1A, 19CKP1A, 19CKIP2A, 19CKP2A, 19CKIP3A | 404, 4XX Oculus deployed | Lebon/Grassia | Y
[6 empty] | 19CKP3A, 19CKP4A, 19CKP5A, 19CKP12A | 401 Oculus recovered
19CKR2A, 19CKR2B, 19CKITAEPR2A
Pop-ups: 201, 202, 203, 204
Plus UAF moorings
MML, AL19_AU_NM1, AL19_AU_BF2, AL19_AU_PH1
AL19_AU_CL1, AL19_AU_IC1, AL19_AU_IC2, AL19_AU_IC3
AL19_AU_PB1, AL19_AU_WT1
OS19-02 | Ocean Starr | 8/25-9/12 | Nome/Nome |  | Load Fisheries Doors, and other equipment |  |  | Donohoe | N
OS19-03 | Ocean Starr | 9/13-10/04 | Nome/Dutch |  |  | MML, AL19_AU_BS2 | 404 Oculus recovered | Strausz | N/A
Pop-ups: 208, 209, 210, 211, 212
Return Shipment Starr to Seattle?
DY19-08 | Oscar Dyson | 9/18-10/08? | Dutch/Kodiak |  | Ship early Sept | 19BS2C, 19BSP2B, 19BS4B, 19BSP4A | 4XX Oculus recovered | Lebon | Y
19BS5A, 19BSP5A, 19BS8A, 19BSP8A, 19CB1B
Plus MML, AL19_AU_BS1, AL19_AU_BS3??
Pop-ups: 205, 206, 207, 213, 214, 215, 216, 217, 218, 219, 220, 221, 222, 223
Return Shipment on Dyson to lower 48
TBD | Pacific Knight |  | Dutch/Dutch |  | June? | 75 kHz ADCP, 300 kHz ADCP | none | Lebon | N