## Data Details
| NRS01 | NRS02 | NRS03 | NRS04 | NRS05 | NRS06 | NRS07 | NRS08 | NRS09 | NRS10 | NRS11 | NRS12
| AK Arctic | Gulf of AK | Olympic Coast (WA) | HI | Channel Islands (CA) | Gulf of MX | SE US (FL) | NE US (MA) | SBNMS | American Samoa | Cordell Bank (CA) | Virgin Islands
1st Deployment
Deployment Date | 2014-10-01 | 2015-01-02 | 2014-09-21 | 2015-07-01 | 2014-10-17 | 2014-07-30 | 2015-04-19 | 2014-06-11 | 2014-10-28 | 2015-06-09 | 2015-10-12 | 2016-11-17
Recording Start Date (if different than Deployment Date) | 2014-10-15 | 2015-01-10 | 2014-10-01 | 2015-07-02 | 2014-10-18 | 2014-08-01 | Recording failure | 2014-05-23 | 2014-10-21 | 2015-06-15 | 2015-10-17 | 2016-08-20
Planned recovery/max logging | bar: NRS01 to NRS12
Recovery Date | 2015-09-16 | 2016-08-26 | 2015-10-01 | 07/?/2017 | 2015-11-05 | 2016-04-11 | 2016-08-20 | 2016-04-23 | 2015-09-17 | 2016-08-18 | 2017-10-04 | 2017-05-02
Recording End Date (if different than Recovery Date) | 2015-10-26 | 2015-11-03 | 2015-07-24 | 2016-12-23 | 2015-08-10 | 2016-03-15 | Recording failure | 2015-02-19 | 2015-08-13 | 2016-04-05 | 2017-10-09 | 2017-06-05
Initial Data Quality check (e.g. successfully recorded with acoustic data) | Ok (SMH) | Rec issues (SMH) | Ok (SMH) | Saturated? (SMH) | Ok (SMH) | Ok (SMH) | N/A | Ok (SMH) | Ok (SMH) | Ok (SMH) | Ok (SMH) | Ok
Clipping assessment (Y/N) | bar: NRS01; NRS03 to NRS09
Diagnosis/reason for clipping (e.g., mooring related, noise sources) | NRS02: Insturment failure
Distributed to NOAA Partners (Y/N & who) | Y(PMEL/OST/NEFSC | N | Y(PMEL/OST/NEFSC |  | Y(PMEL/OST/NEFSC | Y(PMEL/OST/NEFSC |  | Y(PMEL/OST/NEFSC | Y(PMEL/OST/NEFSC | Y(PMEL/OST/NPS) |  | Y(NPS)
Needs Navy Clearance (Y/N) | bar: NRS01 to NRS12
If so, Clearance Status (Sent/Not yet Sent, Cleared-Complete, Cleared-with Redactions) | NA | NA | Cleared-with Redactions | Cleared-with Redactions | Cleared-Complete | NA | N/A | Cleared-Complete | NA | NA | NA | NA
NCEI archive status of Cleared Data (Converted to WAV files, Packaged-using Standalone packager or Tethys for metadata, Sent) | Y | Y | Y | N/A | Y | Y | N/A | Y | Y | Y | Y | Y
Initial Analyses (TBD) Conducted (Y/N) | Y | N/A | Y | N/A | Y | Y | N/A | Y | Y | Y | Y | Y
2nd Deployment
Deployment Date | 2015-09-16 | 2016-08-26 | 2015-10-01 | 07/?/2017 | 2015-11-05 | 2016-04-11 | 2016-08-20 | 2016-04-23 | 2015-09-17 | 2016-08-18 | 2017-10-04 | 2017-05-02
Recording Start Date (if different than Deployment Date) | 2015-10-15 | 2016-06-19 | 2015-09-15 | 2017-07-14 | 2015-11-12 | 2016-04-02 | 2016-06-15 | 2016-03-22 | 2015-09-23 | 2016-07-15 | 2017-10-04 | 2017-05-06
Planned recovery/max logging | - | 2018-07-01 | - | - | 2017-11-12 | - | 2018-06-15 | - | - | - | - | -
Recovery Date | 2017-08-31 | N/A | 2017-09-21 | Spring 2020 | Release failure (10/2017) | 2018-03-09 | N/A | 2018-06-10 | 2016-11-09 | 2017-07-27 | 2019-10-24 | 2018-05-22
Recording End Date (if different than Recovery Date) | 2017-10-25 | Equipment failure | Equipment failure | 2019-07-24 | Equipment failure |  | Equipment failure |  | Equipment failure | 2016-11-13 |  | 2018-05-22
Initial Data Quality check (e.g. successfully recorded with acoustic data) |  | Equipment failure | Equipment failure | Ok | Equipment failure |  | Equipment failure |  | Equipment failure | Recovered |  | Ok (SMH)
Clipping assessment (Y/N) | NRS02: N/A; NRS03: N/A; NRS05: N/A; NRS07: N/A; NRS09: N/A; NRS10: N/A
Diagnosis/reason for clipping (e.g., mooring related, noise sources) | NRS02: Mooring failure/unable to recover; NRS03: AUH flooded; NRS05: Mooring failure/unable to recover; NRS07: Mooring failure/unable to recover; NRS09: AUH flooded
Needs Navy Clearance (Y/N) | bar: NRS01 to NRS12
If so, Clearance Status (Sent/Not yet Sent, Cleared-Complete, Cleared-with Redactions) | NA | NA | NA | Sent (AL) | N/A | NA | NA |  | NA | NA | NA | NA
NCEI archive status of Cleared Data (Converted to WAV files, Packaged-using Standalone packager or Tethys for metadata, Sent) | Y | N/A | N/A |  | N/A | Y | N/A | Y | N/A | Y |  | Y
Initial Analyses (TBD) Conducted (Y/N) | NRS02: N/A; NRS03: N/A; NRS05: N/A; NRS07: N/A; NRS09: N/A; NRS10: Y; NRS12: Y
3rd Deployment
Deployment Date | 2018-08-20 | 2018-07-29 | 2017-09-21 | March 2020? | 2018-01-17 | 2018-03-09 | 2019-06-16 | 2018-06-10 | 2016-11-10 | 2017-07-27 | 2019-10-24 | 2018-05-23
Recording Start Date (if different than Deployment Date) | 2018-08-14 | 2018-07-20 | 2017-09-18 |  | 2018-01-16 | 2018-03-15 |  | 2018-06-09 | 2016-11-08 | 2017-06-15
Planned recovery/max logging | - | - | - | 2022-03-01 | - | - | 2021-06-01 | Attempted 10/4/2020 | - | - | 2021-10-01 | -
Recovery Date | 2020-09-15 | 2020-08-16 | 2019-09-11 |  | 2019-12-19 | 2020-08-14 |  | Equipment failure | 2017-11-18 | 2019-03-12 |  | 2019-05-23
Recording End Date (if different than Recovery Date) | NRS08: Equipment failure; NRS09: 2018-01-26; NRS10: 2018-09-02
Initial Data Quality check (e.g. successfully recorded with acoustic data) | OK - LR | Ok | Ok |  | Ok | Ok - LR |  | N/A | Ok | Ok |  | Ok
Distributed to NOAA Partners (Y/N & who) | NRS08: Mooring failure/unable to recover
Needs Navy Clearance (Y/N) | bar: NRS01 to NRS12
If so, Clearance Status (Sent/Not yet Sent, Cleared-Complete, Cleared-with Redactions) | NA | Sent upon request (AL) | Sent (AL) |  |  | NA |  | N/A | NA | NA | NA | NA
NCEI archive status of Cleared Data (Converted to WAV files, Packaged-using Standalone packager or Tethys for metadata, Sent) | Pending | Pending | Pending |  | Pending | Pending |  | N/A | Y | Y |  | Pending
Initial Analyses (TBD) Conducted (Y/N) | NRS08: N/A
4th Deployment
Deployment Date | 2020-09-15 | 2020-08-16 | 2019-09-11 |  | 2019-12-19 | 2020-08-14 |  | 2020-10-04 | 2018-01-19 | 2019-03-12 |  | 2019-05-23
Recording Start Date (if different than Deployment Date) | NRS06: 2020-08-14; NRS09: 2017-10-10; NRS10: 2018-08-31; NRS12: 2019-05-14
Planned recovery/max logging | Sept 2021 | 2022-08-01 | - |  | 2021-12-01 | 2022-08-15 |  | 2022-10-01 | - | Spring 2020 - delayed, equipment local
Recovery Date | NRS03: 2020-07-31; NRS09: 2018-12-05; NRS12: 2020-12-03
Recording End Date (if different than Recovery Date) | NRS09: 2018-06-16; NRS12: 2021-01-27
Initial Data Quality check (e.g. successfully recorded with acoustic data) | bar: NRS03; NRS09
Distributed to NOAA Partners (Y/N & who)
Needs Navy Clearance (Y/N) | bar: NRS01 to NRS11
If so, Clearance Status (Sent/Not yet Sent, Cleared-Complete, Cleared-with Redactions) | NRS01: NA; NRS02: NA; NRS03: Sent; NRS06: NA; NRS09: NA; NRS10: NA; NRS11: NA
NCEI archive status of Cleared Data (Converted to WAV files, Packaged-using Standalone packager or Tethys for metadata, Sent) | bar: NRS09
Initial Analyses (TBD) Conducted (Y/N) | NRS03: Y - Andy/Bob
5th Deployment
Deployment Date | NRS03: 2020-07-31; NRS09: 2018-12-05; NRS12: 2020-12-05
Recording Start Date (if different than Deployment Date) | NRS09: 2018-12-02
Planned recovery/max logging | NRS03: 2022-07-01; NRS09: -; NRS12: Fall 2021?
Recovery Date | NRS09: 2019-11-26
Recording End Date (if different than Recovery Date)
Initial Data Quality check (e.g. successfully recorded with acoustic data) | bar: NRS09
Distributed to NOAA Partners (Y/N & who)
Needs Navy Clearance (Y/N) | bar: NRS01 to NRS11
If so, Clearance Status (Sent/Not yet Sent, Cleared-Complete, Cleared-with Redactions) | bar: NRS01 to NRS02; NRS06; NRS09 to NRS11
NCEI archive status of Cleared Data (Converted to WAV files, Packaged-using Standalone packager or Tethys for metadata, Sent) | NRS09: Pending
Initial Analyses (TBD) Conducted (Y/N)
6th Deployment
Deployment Date | NRS09: 2019-11-26
Recording Start Date (if different than Deployment Date)
Planned recovery/max logging | NRS09: ~11/17/2020
Recovery Date
Recording End Date (if different than Recovery Date)
Initial Data Quality check (e.g. successfully recorded with acoustic data) | NRS09: OK - LR
Distributed to NOAA Partners (Y/N & who)
Needs Navy Clearance (Y/N) | bar: NRS01 to NRS02; NRS06; NRS09 to NRS11
If so, Clearance Status (Sent/Not yet Sent, Cleared-Complete, Cleared-with Redactions) | bar: NRS01 to NRS02; NRS06; NRS09 to NRS11
NCEI archive status of Cleared Data (Converted to WAV files, Packaged-using Standalone packager or Tethys for metadata, Sent)
Initial Analyses (TBD) Conducted (Y/N)
7th Deployment
Deployment Date | NRS09: ~11/17/2020
Recording Start Date (if different than Deployment Date)
Planned recovery/max logging
Recovery Date
Recording End Date (if different than Recovery Date)
Initial Data Quality check (e.g. successfully recorded with acoustic data)
Distributed to NOAA Partners (Y/N & who)
Needs Navy Clearance (Y/N) | bar: NRS01 to NRS02; NRS06; NRS09 to NRS11
If so, Clearance Status (Sent/Not yet Sent, Cleared-Complete, Cleared-with Redactions) | bar: NRS01 to NRS02; NRS06; NRS09 to NRS11
NCEI archive status of Cleared Data (Converted to WAV files, Packaged-using Standalone packager or Tethys for metadata, Sent)
Initial Analyses (TBD) Conducted (Y/N)
8th Deployment
Deployment Date
Recording Start Date (if different than Deployment Date)
Planned recovery/max logging
Recovery Date
Recording End Date (if different than Recovery Date)
Initial Data Quality check (e.g. successfully recorded with acoustic data)
Distributed to NOAA Partners (Y/N & who)
Needs Navy Clearance (Y/N) | bar: NRS01 to NRS02; NRS06; NRS09 to NRS11
If so, Clearance Status (Sent/Not yet Sent, Cleared-Complete, Cleared-with Redactions) | bar: NRS01 to NRS02; NRS06; NRS09 to NRS11
NCEI archive status of Cleared Data (Converted to WAV files, Packaged-using Standalone packager or Tethys for metadata, Sent)
Initial Analyses (TBD) Conducted (Y/N)

## NRS status Gantt chart
Site | NRS01 (Alaskan Arctic)
NRS02 (Gulf of Alaska)
NRS03 (Olympic Coast)
NRS04 (Hawaiian Islands)
NRS05 (Channel Islands)
| NRS06 (Gulf of Mexico) | [71 empty] | Need to conf. end. date
NRS07 (SE US)
NRS08 (NE US)
NRS09 (Stellwagen Bank)
NRS10 (American Samoa)
NRS11 (Cordell Bank)
NRS12 (US VI)
|  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | 2014 | [7 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
Year
Key
No data
Recording/Mooring failure
In-water
Data available
Data not yet availible