## FY19 Research Cruise Schedule
Start Date | End Date | Port - Depart | Port - Arrive | DAS | Cruise Location | Personnel | Name: Activities | Project | Ship & Cruise No. | Cruise Plan/Instructions | Cruise Report/Summary | Cruise Statistics | CTD Logs | Land POC | NOAA Teacher at Sea Program | Shipment POC | Shipment Drop-dead Date (for Details see 'Operation Timeline' tab in this document) | Nutrient POC | LAST UPDATE: | 2026-08-05 | 15:12
2019-01-29 | 2019-01-30 | Seattle, WA | Seattle, WA | 0 | Puget Sound | Chief Scientist: TBD; 0 (AFSC) TBD; 0 (PMEL) None; 0 (ABL) | / Gear Trials (OMAO-5410): Equipment: TBD; ITAE Technologies: None; DBO: No | MACE | OMAO-5410 | n/a | n/a | n/a | n/a | J. Napp | None | N/A | 2019-04-05 | TBD
2019-04-19 | 2019-05-02 | Kodiak, AK | Dutch Harbor, AK | 14 | Bering Sea | Chief Scientist: P. Proctor; 2 (AFSC) M. Paquin (FPC), L. Rogers; 4 (PMEL) G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe; 1 (ABL) L. Eisner | Spring Mooring/ FOCI Moorings - Bering Sea (DY19-04): Equipment: Moorings (w/ Prawler), CTD, bongo, CalVet, towfish; ITAE Technologies: Oculus (401 deploy, 40X back-up); DBO: No | NPCREP, EcoFOCI | DY19-04 | no | no | no | no | P. Stabeno | None | G. Lebon | TBD | P. Proctor
2019-05-05 | 2019-05-25 | Dutch Harbor, AK | Kodiak, AK | 21 | Gulf of Alaska | Chief Scientist: A. Doughherty; 4 (AFSC) S. Porter, J. Lamb, C. Harpold; 0 (PMEL) None; 1 (ABL) | WGOA Ichthyoplankton/ EMA-FOCI Larval Groundfish Assessment (DY19-05): Equipment: neuston, bongo, fastcat, CalVET, drifters; ITAE Technologies: None; DBO: No | NPCREP, EcoFOCI, EMA | DY19-05 | yes | yes | no | no | J. Duffy-Anderson | None | G. Lebon | TBD | TBD
2019-05-05 | 2019-06-08 | Seattle, WA | Kodiak, AK | 0 | Gulf of Alaska | Chief Scientist: J. Cross; 0 (AFSC) None; 2 (PMEL) D. Strausz; 0 (ABL) None | GOAOA/ Gulf of Alaska Ocean Acidification (Cancelled): Equipment: CTD, bongo; ITAE Technologies: None; DBO: No | OAP | Cancelled | n/a | n/a | n/a | n/a | J.Cross | N/A | N/A | N/A | N/A
2019-07-31 | 2019-08-24 | Dutch Harbor, AK | Nome, AK | 25 | US Arctic: Chukchi Sea | Chief Scientist: R. McCabe; 1 (AFSC) L. Logerwell (FPC); 3 (PMEL) S. Donohoe, C. Berchock, D. Strausz; 1 (ABL) L. Eisner | Arctic Integrated Ecosystem Survey: MOORINGS Leg 1/ NPRB Arctic IERP (OS19-01 Leg 1): Equipment: acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (401 recover & 404 deploy), Pop-up (4), RAS mooring (1), SM Prawler (TBD); DBO: Yes | NPRB AIERP | OS19-01 Leg 1 | no | no | no | no | E. Farley | None | G. Lebon | TBD | P. Proctor
2019-08-02 | 2019-08-23 | Barrow, AK | Barrow, AK | 22 | US Arctic: Chukchi Sea | Chief Scientist: B. Pickart; 2 (AFSC) J. Duffy-Anderson, Benson, Hayes (Sea Grant); 1 (PMEL) E. Wisegarver ; 0 (ABL) | DBO-NCIS Moorings/ NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) (HL19-00): Equipment: CTD, bongo; ITAE Technologies: TBD; DBO: Yes | EcoFOCI & ITAE | HL19-00 | no | no | no | no | R. Crain | None | G. Lebon | TBD | P. Proctor
2019-08-13 | 2019-08-26 | Kodiak, AK | Kodiak, AK | 14 | Gulf of Alaska | Chief Scientist: M. Wilson; 4 (AFSC) L. Rogers, M. Busby, A. Deary; 1 (PMEL) H. Tabisola; 2 (ABL) W. Strasburger, D. Nicolls, C. Harris (TAS) | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 1): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA, EcoFOCI | DY19-07 Leg 1 | yes | no | no | no | J. Duffy-Anderson | 1 | M. Wilson | TBD | TBD
2019-08-25 | 2019-09-14 | Nome, AK | Nome, AK | 21 | US Arctic: Chukchi Sea | Chief Scientist: E. Farley; TBD (AFSC) L. Logerwel (FPC), D. Cooper, D. Kimmel; 1 (PMEL) S. Donohoe; 4 (ABL) | Arctic Integrated Ecosystem Survey: TRAWLING Leg 2/ NPRB Arctic IERP (OS19-01 Leg 2): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: None; DBO: Yes | NPRB AIERP | OS19-01 Leg 2 | no | no | no | no | E. Farley | None | S. Donohoe/Kris Cieciel | TBD | P. Proctor
2019-08-29 | 2019-09-14 | Kodiak, AK | Dutch Harbor, AK | 17 | Gulf of Alaska | Chief Scientist: S. Porter; 4 (AFSC) A. Dougherty, M. Paquin, C. Harpold; 1 (PMEL) P. Proctor; 3 (ABL) J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS) | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 2): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA, EcoFOCI | DY19-07 Leg 2 | yes | no | no | no | J. Duffy-Anderson | 1 | S. Porter | TBD | TBD
2019-09-13 | 2019-10-02 | Nome, AK | Dutch Harbor, AK | 20 | US Arctic: Chukchi Sea | Chief Scientist: K. Cieciel; 1 (AFSC) D. Cooper (FPC), A. Spear, E. Goldstein; 1 (PMEL) D. Strausz; 4 (ABL) | Arctic Integrated Ecosystem Survey: TRAWLING Leg 3/ NPRB Arctic IERP (OS19-01 Leg 3): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (404 recover), Pop-up (TBD); DBO: Yes | NPRB AIERP | OS19-01 Leg 3 | no | no | no | no | E. Farley | None | D. Strausz | TBD | P. Proctor
2019-09-18 | 2019-10-02 | Dutch Harbor, AK | Kodiak, AK | 15 | Bering Sea | Chief Scientist: P. Proctor; 2 (AFSC) J. Lamb, A. Deary; 7 (PMEL) G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson; 0 (ABL) | Fall Mooring/ FOCI Moorings - Bering Sea (DY19-08): Equipment: Moorings, CTD, bongo, CalVet; ITAE Technologies: Oculus (B recover), Pop-up (TBD); DBO: Yes | EMA, EcoFOCI | DY19-08 | no | no | no | no | P. Stabeno | None | G. Lebon | TBD | P. Proctor
TBD | TBD | Sitka, AK | Juneau, AK | TBD | Gulf of Alaska | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5 (ABL) | EGOA SECM Survey/ Eastern Gulf of Alaska(EGOA) Southeast Alaska Coastal Monitoring (SECM) Survey (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA | XX19-00 |  |  |  |  | TBD | None | TBD | TBD | TBD
TBD | TBD | Dutch Harbor, AK | Dutch Harbor, AK | TBD | US Arctic: Bering Sea | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5-6 (ABL) | EMA/ADFG NBS/ Joint AFSC/ADFG research/ EMA/ADFG NBS/ Joint AFSC/ADFG research (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA | XX19-00 |  |  |  |  | TBD | None | J. Lamb | TBD | TBD
2019-07-12 | 2019-08-01 | Dutch Harbor, AK | Dutch Harbor, AK | 21 | US Arctic: Bering Sea | Chief Scientist: C. Wilson; 0 (AFSC) None; 0 (PMEL) None; 0 (ABL) | Eastern Bering Sea Bottom Trawl Survey Leg 3/ Eastern Bering Sea Bottom Trawl Survey (AK19-01): Equipment: moorings; ITAE Technologies: None; DBO: No | MACE | AK19-01 |  |  |  |  | C. Wilson | None | G. Lebon | TBD | N/A
Note on A1: +sarah.s.donohoe@noaa.gov Can you come chat with me when you have a chance. This is a duplicate sheet. The Blue Tab was designed for the website, and if that's not what your using, let's devise a way to streamline this to avoid duplicate schedules for the same purpose, in here. :) _Assigned to you_ -Heather Tabisola - NOAA Affiliate Hi Heather! This is a sheet I made for quick at-a-glance info for the cruises, and it is the same thing I use to update the internal webpage. -Sarah Donohoe - NOAA Federal Yes. It's a dulicate to the first tab :) Come chat when you can. -Heather Tabisola - NOAA Affiliate Hey! OK, chatted with Phyllis and Janet. Both would like, at present, to keep the historical way of viewing the sheet (tab one in this doc). But, are open to discussion this summer about how to best manage the website in regards to schedule. They did agree a link above the current one, is the best way to start to transition folks, for the few who actually use the field season internal site. One step at a time :) With that, please mark this conversation as 'read' and delete the tab when done. Or let me know, and I will delete it. -Heather Tabisola - NOAA Affiliate Hello Heather, Thanks for asking Phyllis and Janet, I will delete the duplicate sheet. -Sarah Donohoe - NOAA Federal

## FY19_Webpage
Start Date | End Date | Port - Depart | Port - Arrive | DAS | Cruise Location | Personnel | Name: Activities | Project | Ship & Cruise No.
2019-01-29 | 2019-01-30 | Seattle, WA | Seattle, WA | 0 | Puget Sound | Chief Scientist: TBD; 0 (AFSC) TBD; 0 (PMEL) None; 0 (ABL) | / Gear Trials (OMAO-5410): Equipment: TBD; ITAE Technologies: None; DBO: No | MACE | OMAO-5410
2019-04-19 | 2019-05-02 | Kodiak, AK | Dutch Harbor, AK | 14 | Bering Sea | Chief Scientist: P. Proctor; 2 (AFSC) M. Paquin (FPC), L. Rogers; 4 (PMEL) G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe; 1 (ABL) L. Eisner | Spring Mooring/ FOCI Moorings - Bering Sea (DY19-04): Equipment: Moorings (w/ Prawler), CTD, bongo, CalVet, towfish; ITAE Technologies: Oculus (401 deploy, 40X back-up); DBO: No | NPCREP, EcoFOCI | DY19-04
2019-05-05 | 2019-05-25 | Dutch Harbor, AK | Kodiak, AK | 21 | Gulf of Alaska | Chief Scientist: A. Doughherty; 4 (AFSC) S. Porter, J. Lamb, C. Harpold; 0 (PMEL) None; 1 (ABL) | WGOA Ichthyoplankton/ EMA-FOCI Larval Groundfish Assessment (DY19-05): Equipment: neuston, bongo, fastcat, CalVET, drifters; ITAE Technologies: None; DBO: No | NPCREP, EcoFOCI, EMA | DY19-05
2019-05-05 | 2019-06-08 | Seattle, WA | Kodiak, AK | 0 | Gulf of Alaska | Chief Scientist: J. Cross; 0 (AFSC) None; 2 (PMEL) D. Strausz; 0 (ABL) None | GOAOA/ Gulf of Alaska Ocean Acidification (Cancelled): Equipment: CTD, bongo; ITAE Technologies: None; DBO: No | OAP | Cancelled
2019-07-31 | 2019-08-24 | Dutch Harbor, AK | Nome, AK | 25 | US Arctic: Chukchi Sea | Chief Scientist: R. McCabe; 1 (AFSC) L. Logerwell (FPC); 3 (PMEL) S. Donohoe, C. Berchock, D. Strausz; 1 (ABL) L. Eisner | Arctic Integrated Ecosystem Survey: MOORINGS Leg 1/ NPRB Arctic IERP (OS19-01 Leg 1): Equipment: acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (401 recover & 404 deploy), Pop-up (4), RAS mooring (1), SM Prawler (TBD); DBO: Yes | NPRB AIERP | OS19-01 Leg 1
2019-08-02 | 2019-08-23 | Barrow, AK | Barrow, AK | 22 | US Arctic: Chukchi Sea | Chief Scientist: B. Pickart; 2 (AFSC) J. Duffy-Anderson, Benson, Hayes (Sea Grant); 1 (PMEL) E. Wisegarver ; 0 (ABL) | DBO-NCIS Moorings/ NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) (HL19-00): Equipment: CTD, bongo; ITAE Technologies: TBD; DBO: Yes | EcoFOCI & ITAE | HL19-00
2019-08-13 | 2019-08-26 | Kodiak, AK | Kodiak, AK | 14 | Gulf of Alaska | Chief Scientist: M. Wilson; 4 (AFSC) L. Rogers, M. Busby, A. Deary; 1 (PMEL) H. Tabisola; 2 (ABL) W. Strasburger, D. Nicolls, C. Harris (TAS) | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 1): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA, EcoFOCI | DY19-07 Leg 1
2019-08-25 | 2019-09-14 | Nome, AK | Nome, AK | 21 | US Arctic: Chukchi Sea | Chief Scientist: E. Farley; TBD (AFSC) L. Logerwel (FPC), D. Cooper, D. Kimmel; 1 (PMEL) S. Donohoe; 4 (ABL) | Arctic Integrated Ecosystem Survey: TRAWLING Leg 2/ NPRB Arctic IERP (OS19-01 Leg 2): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: None; DBO: Yes | NPRB AIERP | OS19-01 Leg 2
2019-08-29 | 2019-09-14 | Kodiak, AK | Dutch Harbor, AK | 17 | Gulf of Alaska | Chief Scientist: S. Porter; 4 (AFSC) A. Dougherty, M. Paquin, C. Harpold; 1 (PMEL) P. Proctor; 3 (ABL) J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS) | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 2): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA, EcoFOCI | DY19-07 Leg 2
2019-09-13 | 2019-10-02 | Nome, AK | Dutch Harbor, AK | 20 | US Arctic: Chukchi Sea | Chief Scientist: K. Cieciel; 1 (AFSC) D. Cooper (FPC), A. Spear, E. Goldstein; 1 (PMEL) D. Strausz; 4 (ABL) | Arctic Integrated Ecosystem Survey: TRAWLING Leg 3/ NPRB Arctic IERP (OS19-01 Leg 3): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (404 recover), Pop-up (TBD); DBO: Yes | NPRB AIERP | OS19-01 Leg 3
2019-09-18 | 2019-10-02 | Dutch Harbor, AK | Kodiak, AK | 15 | Bering Sea | Chief Scientist: P. Proctor; 2 (AFSC) J. Lamb, A. Deary; 7 (PMEL) G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson; 0 (ABL) | Fall Mooring/ FOCI Moorings - Bering Sea (DY19-08): Equipment: Moorings, CTD, bongo, CalVet; ITAE Technologies: Oculus (B recover), Pop-up (TBD); DBO: Yes | EMA, EcoFOCI | DY19-08
TBD | TBD | Sitka, AK | Juneau, AK | TBD | Gulf of Alaska | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5 (ABL) | EGOA SECM Survey/ Eastern Gulf of Alaska(EGOA) Southeast Alaska Coastal Monitoring (SECM) Survey (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA | XX19-00
TBD | TBD | Dutch Harbor, AK | Dutch Harbor, AK | TBD | US Arctic: Bering Sea | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5-6 (ABL) | EMA/ADFG NBS/ Joint AFSC/ADFG research/ EMA/ADFG NBS/ Joint AFSC/ADFG research (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EMA | XX19-00
2019-07-12 | 2019-08-01 | Dutch Harbor, AK | Dutch Harbor, AK | 21 | US Arctic: Bering Sea | Chief Scientist: C. Wilson; 0 (AFSC) None; 0 (PMEL) None; 0 (ABL) | Eastern Bering Sea Bottom Trawl Survey Leg 3/ Eastern Bering Sea Bottom Trawl Survey (AK19-01): Equipment: moorings; ITAE Technologies: None; DBO: No | MACE | AK19-01

## SHIPPING LOGISTICS & TIMELINE
Cruise No. | Vessel | Cruise Dates | Depart Port | Arrive Port | Drop-dead Date | Shipment Details/Notes | Vehicles deployed | FOCI/ITAE Moorings Deployed | FOCI/ITAE Moorings Recovered | MML Moorings Deployed | MML Moorings Recovered | Pop-ups Deployed | Shipment POC | Hazmats
OMAO-5410 | NOAAS Oscar Dyson |  | Seattle, WA | Seattle, WA | N/A |  | None | None |  | None |  | None | N/A | N
DY19-04 | NOAAS Oscar Dyson | 04/19/19 - 05/02/19 | Kodiak, AK | Dutch Harbor, AK | 2019-04-08 | Load at pier 91 on the 10th of April... Return Shipment June 2nd from Kodiak by barge following DY19-03 **Return shipment actually arriving July 11th** | Oculus (401 deploy, 40X back-up) | 19CB1A, 19BSM2A, 19BSP2A, 19BSITAEPR-2A (PRAWLER) |  | MML, AL19_AU_BS4, AL19_AU_BS6, AL19_AU_BS3 |  | None | G. Lebon | Y | Done
DY19-05 | NOAAS Oscar Dyson | 05/05/19 - 05/25/19 | Dutch Harbor, AK | Kodiak, AK |  | N/A | None | None |  | None |  | None | G. Lebon | N/A
CANCELLED | R/V Ocean Starr | 05/05/19 - 06/08/19 | Seattle, WA | Kodiak, AK | TBD | N/A | N/A | N/A |  | N/A |  | N/A | J.Cross | N/A
OS19-01 Leg 1 | R/V Ocean Starr | 07/31/19 - 08/24/19 | Dutch Harbor, AK | Nome, AK | TBD | Load at Stabbert. Anchors and heavies load via flat rack on 19 July. Gear trials July 20 and 21. Load remaining gear July 22. |  | 19CKIP1A, 19CKP1A, 19CKIP2A, 19CKP2A, 19CKIP3A, 19CKP3A, 19CKP4A, 19CKP5A, 19CKP12A, 19CKR2A, 19CKITAEPR2A (ICE PRAWLER) |  | MML, AL19_AU_NM1, AL19_AU_BF2, AL19_AU_PH1, AL19_AU_CL1, AL19_AU_IC1, AL19_AU_IC2, AL19_AU_IC3, AL19_AU_PB1, AL19_AU_WT1 |  | None | G. Lebon | Y
HL19-00 | USCGC Healy | 08/02/19 - 08/23/19 | Barrow, AK | Barrow, AK |  | N/A | None | None |  | None |  | None | G. Lebon | N/A
DY19-07 Leg 1 | NOAAS Oscar Dyson | 08/13/19 - 08/26/19 | Kodiak, AK | Kodiak, AK | TBD | Load Fisheries Doors, and other equipment | None | None |  | None |  | None | M. Wilson | N
OS19-01 Leg 2 | R/V Ocean Starr | 08/25/19 - 09/14/19 | Nome, AK | Nome, AK | TBD | Container to Nome, loads at bldg 32 on the 26th of June | None | None |  | Some in the above column will go out on this cruise |  | None | S. Donohoe/Kris Cieciel | N/A
DY19-07 Leg 2 | NOAAS Oscar Dyson | 08/29/19 - 09/14/19 | Kodiak, AK | Dutch Harbor, AK | TBD | N/A | None | None |  | None |  | None | S. Porter | Y
OS19-01 Leg 3 | R/V Ocean Starr | 09/13/19 - 10/02/19 | Nome, AK | Dutch Harbor, AK | TBD | Return ship all equipment on the Ocean Starr |  | None |  | MML, AL19_AU_BS2 |  | Popups: [No. 2] 211, 215 | D. Strausz | N
DY19-08 | NOAAS Oscar Dyson | 09/18/19 - 10/02/19 | Dutch Harbor, AK | Kodiak, AK | TBD | Load containers Aug 27th and 28th; Return Shipment on Dyson to lower 48 |  | 19BS2C, 19BSP2B, 19BS4B, 19BSP4A, 19BS5A, 19BSP5A, 19BS8A, 19BSP8A, 19SHP-1A |  | MML, AL19_AU_BS1, AL19_AU_BS9 |  | Popups: [No. 4] 218, 216, 213, 214 | G. Lebon | Y
XX19-00 | CHARTER TBD | TBD - TBD | Sitka, AK | Juneau, AK |  |  | None | None |  | None |  | None | TBD | N/A
XX19-00 | CHARTER TBD | TBD - TBD | Dutch Harbor, AK | Dutch Harbor, AK |  |  |  | None |  | None |  | None | J. Lamb | N/A
AK19-01 | F/V Alaska Knight | 07/12/19 - 08/01/19 | Dutch Harbor, AK | Dutch Harbor, AK | TBD | 2019-06-12 | None | 75 kHz ADCP, 2 - 300 kHz ADCP, 19BSP-10A, 19BSP-11A, 19BSP-12A |  | None |  | None | G. Lebon | N/A | Done
0 | 0 |  | 0 | 0
0 | 0 |  | 0 | 0
0 | 0 |  | 0 | 0
0 | 0 |  | 0 | 0
0 | 0 |  | 0 | 0
0 | 0 |  | 0 | 0
Note on M5: +geoffrey.t.lebon@noaa.gov are these moving to the updated OS19-01? _Assigned to Geoffrey Lebon - NOAA Affiliate_ -Heather Tabisola - NOAA Affiliate
Note on M6: +sarah.s.donohoe@noaa.gov & +calvin.w.mordy@noaa.gov Edit these when you decide :) _Assigned to you_ -Heather Tabisola - NOAA Affiliate

## FY19 Planning
Research Cruise Title | Alternative Research Cruise Title | Vessel | Cruise No. | Cruise Info | Start Date | End Date | Days at Sea | Depart Port | Arrive Port | Line Office | Research Programs | Research Description | EcoFOCI Equipment | ITAE Technologies | Vehicles Deployed | DBO | Activities: Contencate | Land POC | No. of EcoFOCI Personnel (AFSC/SEA) | No. of of EcoFOCI Personnel (PMEL) | No. of RPA Personnel (ABL) | No. of Other Personnel | NOAA Teacher at Sea Program | Total Personnel | Chief Scientist | AFSC Personnel | PMEL Personnel | ABL Personnel | Concatenate | Shipment POC | Shipment Details | Nutrient Samples POC
Gear Trials |  | NOAAS Oscar Dyson | OMAO-5410 | Puget Sound | 2019-01-29 | 2019-01-30 | 0 | Seattle, WA | Seattle, WA | OMAO | MACE | Gear Trials | TBD | None | None | No | / Gear Trials (OMAO-5410): Equipment: TBD; ITAE Technologies: None; DBO: No | J. Napp | 0 | 0 | 0 | 0 | None | 0 | TBD | TBD | None |  | Chief Scientist: TBD; 0 (AFSC) TBD; 0 (PMEL) None; 0 (ABL) | N/A | TBD | TBD
FOCI Moorings - Bering Sea | Spring Mooring | NOAAS Oscar Dyson | DY19-04 | Bering Sea | 2019-04-19 | 2019-05-02 | 14 | Kodiak, AK | Dutch Harbor, AK | OAR | NPCREP, EcoFOCI | 70m isobath, Moorings: M2, M2 Prawler, M4, M5 & St. Matt. Prawler, CB1A turnaround, Deploy St. Matt's Oculus 401 | Moorings (w/ Prawler), CTD, bongo, CalVet, towfish | Oculus (401 deploy, 40X back-up) | Oculus (401 deploy, 40X back-up) | No | Spring Mooring/ FOCI Moorings - Bering Sea (DY19-04): Equipment: Moorings (w/ Prawler), CTD, bongo, CalVet, towfish; ITAE Technologies: Oculus (401 deploy, 40X back-up); DBO: No | P. Stabeno | 2 | 4 | 1 | 0 | None | 0 | P. Proctor | M. Paquin (FPC), L. Rogers | G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe | L. Eisner | Chief Scientist: P. Proctor; 2 (AFSC) M. Paquin (FPC), L. Rogers; 4 (PMEL) G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe; 1 (ABL) L. Eisner | G. Lebon | TBD | P. Proctor
EMA-FOCI Larval Groundfish Assessment | WGOA Ichthyoplankton | NOAAS Oscar Dyson | DY19-05 | Gulf of Alaska | 2019-05-05 | 2019-05-25 | 21 | Dutch Harbor, AK | Kodiak, AK | NMFS | NPCREP, EcoFOCI, EMA |  | neuston, bongo, fastcat, CalVET, drifters | None | None | No | WGOA Ichthyoplankton/ EMA-FOCI Larval Groundfish Assessment (DY19-05): Equipment: neuston, bongo, fastcat, CalVET, drifters; ITAE Technologies: None; DBO: No | J. Duffy-Anderson | 4 | 0 | 1 | 1 | None | 0 | A. Doughherty | S. Porter, J. Lamb, C. Harpold | None |  | Chief Scientist: A. Doughherty; 4 (AFSC) S. Porter, J. Lamb, C. Harpold; 0 (PMEL) None; 1 (ABL) | G. Lebon | TBD | TBD
Gulf of Alaska Ocean Acidification | GOAOA | R/V Ocean Starr | Cancelled | Gulf of Alaska | 2019-05-05 | 2019-06-08 | 0 | Seattle, WA | Kodiak, AK | OAR | OAP | Coastal ocean acidification program, follow-on of 2015, continuous CTD sampling | CTD, bongo | None | None | No | GOAOA/ Gulf of Alaska Ocean Acidification (Cancelled): Equipment: CTD, bongo; ITAE Technologies: None; DBO: No | J.Cross | 0 | 2 | 0 | 0 | None | 0 | J. Cross | None | D. Strausz | None | Chief Scientist: J. Cross; 0 (AFSC) None; 2 (PMEL) D. Strausz; 0 (ABL) None | J.Cross | 2019-05-01 | P. Proctor
NPRB Arctic IERP | Arctic Integrated Ecosystem Survey: MOORINGS Leg 1 | R/V Ocean Starr | OS19-01 Leg 1 | US Arctic: Chukchi Sea | 2019-07-31 | 2019-08-24 | 25 | Dutch Harbor, AK | Nome, AK | OAR | NPRB AIERP | Oculus: recover 401, deploy B & 404, (B-Saint Matthew & 404-Hannah Shoal/Point hope?), C2 Prawler (TBD), Pop-up (4), Alkalinity Mooring?, RAS mooring, Saildrone rendevous (SM Prawler TBD) | acoustics, CTD, bongo, towfish, moorings | Oculus (401 recover & 404 deploy), Pop-up (4), RAS mooring (1), SM Prawler (TBD) |  | Yes | Arctic Integrated Ecosystem Survey: MOORINGS Leg 1/ NPRB Arctic IERP (OS19-01 Leg 1): Equipment: acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (401 recover & 404 deploy), Pop-up (4), RAS mooring (1), SM Prawler (TBD); DBO: Yes | E. Farley | 1 | 3 | 1 | 0 | None | 0 | R. McCabe | L. Logerwell (FPC) | S. Donohoe, C. Berchock, D. Strausz | L. Eisner | Chief Scientist: R. McCabe; 1 (AFSC) L. Logerwell (FPC); 3 (PMEL) S. Donohoe, C. Berchock, D. Strausz; 1 (ABL) L. Eisner | G. Lebon | TBD | P. Proctor
NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) | DBO-NCIS Moorings | USCGC Healy | HL19-00 | US Arctic: Chukchi Sea | 2019-08-02 | 2019-08-23 | 22 | Barrow, AK | Barrow, AK | OAR | EcoFOCI & ITAE |  | CTD, bongo | TBD | None | Yes | DBO-NCIS Moorings/ NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) (HL19-00): Equipment: CTD, bongo; ITAE Technologies: TBD; DBO: Yes | R. Crain | 2 | 1 | 0 | 0 | None | 0 | B. Pickart | J. Duffy-Anderson, Benson, Hayes (Sea Grant) | E. Wisegarver |  | Chief Scientist: B. Pickart; 2 (AFSC) J. Duffy-Anderson, Benson, Hayes (Sea Grant); 1 (PMEL) E. Wisegarver ; 0 (ABL) | G. Lebon | TBD | P. Proctor
EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes | YOY Pollock | NOAAS Oscar Dyson | DY19-07 Leg 1 | Gulf of Alaska | 2019-08-13 | 2019-08-26 | 14 | Kodiak, AK | Kodiak, AK | NMFS | EMA, EcoFOCI |  | midwater trawl, CTD, bongo | None | None | No | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 1): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | J. Duffy-Anderson | 4 | 1 | 2 | 0 | 1 | 0 | M. Wilson | L. Rogers, M. Busby, A. Deary | H. Tabisola | W. Strasburger, D. Nicolls, C. Harris (TAS) | Chief Scientist: M. Wilson; 4 (AFSC) L. Rogers, M. Busby, A. Deary; 1 (PMEL) H. Tabisola; 2 (ABL) W. Strasburger, D. Nicolls, C. Harris (TAS) | M. Wilson | TBD | TBD
NPRB Arctic IERP | Arctic Integrated Ecosystem Survey: TRAWLING Leg 2 | R/V Ocean Starr | OS19-01 Leg 2 | US Arctic: Chukchi Sea | 2019-08-25 | 2019-09-14 | 21 | Nome, AK | Nome, AK | OAR | NPRB AIERP |  | surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings | None | None | Yes | Arctic Integrated Ecosystem Survey: TRAWLING Leg 2/ NPRB Arctic IERP (OS19-01 Leg 2): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: None; DBO: Yes | E. Farley | TBD | 1 | 4 | 0 | None | 0 | E. Farley | L. Logerwel (FPC), D. Cooper, D. Kimmel | S. Donohoe |  | Chief Scientist: E. Farley; TBD (AFSC) L. Logerwel (FPC), D. Cooper, D. Kimmel; 1 (PMEL) S. Donohoe; 4 (ABL) | S. Donohoe/Kris Cieciel | TBD | P. Proctor
EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes | YOY Pollock | NOAAS Oscar Dyson | DY19-07 Leg 2 | Gulf of Alaska | 2019-08-29 | 2019-09-14 | 17 | Kodiak, AK | Dutch Harbor, AK | NMFS | EMA, EcoFOCI |  | midwater trawl, CTD, bongo | None | None | No | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 2): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | J. Duffy-Anderson | 4 | 1 | 3 | 0 | 1 | 0 | S. Porter | A. Dougherty, M. Paquin, C. Harpold | P. Proctor | J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS) | Chief Scientist: S. Porter; 4 (AFSC) A. Dougherty, M. Paquin, C. Harpold; 1 (PMEL) P. Proctor; 3 (ABL) J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS) | S. Porter | TBD | TBD
NPRB Arctic IERP | Arctic Integrated Ecosystem Survey: TRAWLING Leg 3 | R/V Ocean Starr | OS19-01 Leg 3 | US Arctic: Chukchi Sea | 2019-09-13 | 2019-10-02 | 20 | Nome, AK | Dutch Harbor, AK | OAR | NPRB AIERP | Oculus: recover Hannah Shoal/Point Hope Oculus 404, Pop-up Grid Drop (TBD) | surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings | Oculus (404 recover), Pop-up (TBD) |  | Yes | Arctic Integrated Ecosystem Survey: TRAWLING Leg 3/ NPRB Arctic IERP (OS19-01 Leg 3): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (404 recover), Pop-up (TBD); DBO: Yes | E. Farley | 1 | 1 | 4 | 0 | None | 0 | K. Cieciel | D. Cooper (FPC), A. Spear, E. Goldstein | D. Strausz |  | Chief Scientist: K. Cieciel; 1 (AFSC) D. Cooper (FPC), A. Spear, E. Goldstein; 1 (PMEL) D. Strausz; 4 (ABL) | D. Strausz | TBD | P. Proctor
FOCI Moorings - Bering Sea | Fall Mooring | NOAAS Oscar Dyson | DY19-08 | Bering Sea | 2019-09-18 | 2019-10-02 | 15 | Dutch Harbor, AK | Kodiak, AK | OAR, NMFS | EMA, EcoFOCI | 70m isobath, Moorings: M2, M2 Prawler, M4, M5, St. Matt. Prawler, & M8, CB1A turnaround, recover St. Matt's Oculus B, Pop-up Grid Drop (TBD) | Moorings, CTD, bongo, CalVet | Oculus (B recover), Pop-up (TBD) |  | Yes | Fall Mooring/ FOCI Moorings - Bering Sea (DY19-08): Equipment: Moorings, CTD, bongo, CalVet; ITAE Technologies: Oculus (B recover), Pop-up (TBD); DBO: Yes | P. Stabeno | 2 | 7 | 0 | 0 | None | 0 | P. Proctor | J. Lamb, A. Deary | G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson |  | Chief Scientist: P. Proctor; 2 (AFSC) J. Lamb, A. Deary; 7 (PMEL) G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson; 0 (ABL) | G. Lebon | TBD | P. Proctor
Eastern Gulf of Alaska(EGOA) Southeast Alaska Coastal Monitoring (SECM) Survey | EGOA SECM Survey | CHARTER TBD | XX19-00 | Gulf of Alaska | TBD | TBD | TBD | Sitka, AK | Juneau, AK | NMFS | EMA |  | surface trawl, CTD, bongo | None | None | No | EGOA SECM Survey/ Eastern Gulf of Alaska(EGOA) Southeast Alaska Coastal Monitoring (SECM) Survey (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | TBD | 0 | 0 | 5 | 0 | None | 0 | TBD | None | None |  | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5 (ABL) | TBD | TBD | TBD
EMA/ADFG NBS/ Joint AFSC/ADFG research | EMA/ADFG NBS/ Joint AFSC/ADFG research | CHARTER TBD | XX19-00 | US Arctic: Bering Sea | TBD | TBD | TBD | Dutch Harbor, AK | Dutch Harbor, AK | NMFS | EMA |  | surface trawl, CTD, bongo | None | None | No | EMA/ADFG NBS/ Joint AFSC/ADFG research/ EMA/ADFG NBS/ Joint AFSC/ADFG research (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | TBD | 0 | 0 | 5-6 | 0 | None | 0 | TBD | None | None |  | Chief Scientist: TBD; 0 (AFSC) None; 0 (PMEL) None; 5-6 (ABL) | J. Lamb | TBD | TBD
Eastern Bering Sea Bottom Trawl Survey | Eastern Bering Sea Bottom Trawl Survey Leg 3 | F/V Alaska Knight | AK19-01 | US Arctic: Bering Sea | 2019-07-12 | 2019-08-01 | 21 | Dutch Harbor, AK | Dutch Harbor, AK | NMFS | MACE | 75 kHz ADCP, 300 kHz ADCP | moorings | None | None | No | Eastern Bering Sea Bottom Trawl Survey Leg 3/ Eastern Bering Sea Bottom Trawl Survey (AK19-01): Equipment: moorings; ITAE Technologies: None; DBO: No | C. Wilson | 0 | 0 | 0 | 0 | None | 0 | C. Wilson | None | None |  | Chief Scientist: C. Wilson; 0 (AFSC) None; 0 (PMEL) None; 0 (ABL) | G. Lebon | TBD | N/A
[29 empty] | Chief Scientist: P. Proctor; 2 (AFSC) M. Paquin (FPC), L. Rogers; 4 (PMEL) G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe; 1 (ABL) L. EisnerChief Scientist: A. Doughherty; 4 (AFSC) S. Porter, J. Lamb, C. Harpold; 0 (PMEL) None; 1 (ABL) Chief Scientist: R. McCabe; 1 (AFSC) L. Logerwell (FPC); 3 (PMEL) S. Donohoe, C. Berchock, D. Strausz; 1 (ABL) L. EisnerChief Scientist: B. Pickart; 2 (AFSC) J. Duffy-Anderson, Benson, Hayes (Sea Grant); 1 (PMEL) E. Wisegarver ; 0 (ABL) Chief Scientist: M. Wilson; 4 (AFSC) L. Rogers, M. Busby, A. Deary; 1 (PMEL) H. Tabisola; 2 (ABL) W. Strasburger, D. Nicolls, C. Harris (TAS)Chief Scientist: E. Farley; TBD (AFSC) L. Logerwel (FPC), D. Cooper, D. Kimmel; 1 (PMEL) S. Donohoe; 4 (ABL) Chief Scientist: S. Porter; 4 (AFSC) A. Dougherty, M. Paquin, C. Harpold; 1 (PMEL) P. Proctor; 3 (ABL) J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS)Chief Scientist: K. Cieciel; 1 (AFSC) D. Cooper (FPC), A. Spear, E. Goldstein; 1 (PMEL) D. Strausz; 4 (ABL) Chief Scientist: P. Proctor; 2 (AFSC) J. Lamb, A. Deary; 7 (PMEL) G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson; 0 (ABL) | Chief Scientist: P. Proctor; 2 (AFSC) M. Paquin (FPC), L. Rogers; 4 (PMEL) G. Lebon or Engineering, S. Grassia, S. Bell, S. Donohoe; 1 (ABL) L. EisnerChief Scientist: A. Doughherty; 4 (AFSC) S. Porter, J. Lamb, C. Harpold; 0 (PMEL) None; 1 (ABL) Chief Scientist: R. McCabe; 1 (AFSC) L. Logerwell (FPC); 3 (PMEL) S. Donohoe, C. Berchock, D. Strausz; 1 (ABL) L. EisnerChief Scientist: B. Pickart; 2 (AFSC) J. Duffy-Anderson, Benson, Hayes (Sea Grant); 1 (PMEL) E. Wisegarver ; 0 (ABL) Chief Scientist: M. Wilson; 4 (AFSC) L. Rogers, M. Busby, A. Deary; 1 (PMEL) H. Tabisola; 2 (ABL) W. Strasburger, D. Nicolls, C. Harris (TAS)Chief Scientist: E. Farley; TBD (AFSC) L. Logerwel (FPC), D. Cooper, D. Kimmel; 1 (PMEL) S. Donohoe; 4 (ABL) Chief Scientist: S. Porter; 4 (AFSC) A. Dougherty, M. Paquin, C. Harpold; 1 (PMEL) P. Proctor; 3 (ABL) J. Moss, R. Suryan, O. Ormseth, P. Moorhouse (TAS)Chief Scientist: K. Cieciel; 1 (AFSC) D. Cooper (FPC), A. Spear, E. Goldstein; 1 (PMEL) D. Strausz; 4 (ABL) Chief Scientist: P. Proctor; 2 (AFSC) J. Lamb, A. Deary; 7 (PMEL) G. Lebon, S. Grassia, J. Law, E. Wisegarver, B. Kimber, S. Bell, S. Anderson; 0 (ABL)

## FY19 Summary of Operations
Cruise No. | Research Cruise Title | Chief Scientist | Days at Sea | Research Programs | DBO | No. of EcoFOCI Personnel (AFSC/SEA) | No. of of EcoFOCI Personnel (PMEL) | No. of RPA Personnel (ABL) | No. of Other Personnel | NOAA Teacher at Sea Program | Operations: Bongo Tows | Operations: PMEL Moorings Deployed | Operations: PMEL Mooring Recovered | Operations: Other Moorings deployed/ recovered | Operations: CTD (CTD & CTDB) | RZA
OMAO-5410 | Gear Trials | TBD | 0 | MACE | No | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0
DY19-04 | FOCI Moorings - Bering Sea | P. Proctor | 14 | NPCREP, EcoFOCI | No | 2 | 4 | 1 | 0 | None
DY19-05 | EMA-FOCI Larval Groundfish Assessment | A. Doughherty | 21 | NPCREP, EcoFOCI, EMA | No | 4 | 0 | 1 | 1 | None | 232 | 0 | 0 | 0 | 25 | 124
Cancelled | Gulf of Alaska Ocean Acidification | J. Cross | 0 | OAP | No | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0 | 0
OS19-01 Leg 1 | NPRB Arctic IERP | R. McCabe | 25 | NPRB AIERP | Yes | 1 | 3 | 1 | 0 | None
HL19-00 | NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) | B. Pickart | 22 | EcoFOCI & ITAE | Yes | 2 | 1 | 0 | 0 | None
DY19-07 Leg 1 | EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes | M. Wilson | 14 | EMA, EcoFOCI | No | 4 | 1 | 2 | 0 | 1 | 125 | 0 | 0 | 0 | 19 | 118
OS19-01 Leg 2 | NPRB Arctic IERP | E. Farley | 21 | NPRB AIERP | Yes | TBD | 1 | 4 | 0 | None
DY19-07 Leg 2 | EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes | S. Porter | 17 | EMA, EcoFOCI | No | 4 | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
OS19-01 Leg 3 | NPRB Arctic IERP | K. Cieciel | 20 | NPRB AIERP | Yes | 1 | 1 | 4 | 0 | None
DY19-08 | FOCI Moorings - Bering Sea | P. Proctor | 15 | EMA, EcoFOCI | Yes | 2 | 7 | 0 | 0 | None
XX19-00 |  | TBD | 0 | EMA | No | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0 | 0
XX19-00 |  | TBD | 0 | EMA | No | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0 | 0
AK19-01 |  | C. Wilson | 0 | MACE | No | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 0 | 0
0 |  |  | 0 | 0
0 |  |  | 0 | 0
0 |  |  | 0 | 0
0 |  |  | 0 | 0
0 |  |  | 0 | 0
0 |  |  | 0 | 0
0 |  |  | 0 | 0
0 |  |  | 0 | 0
0 |  |  | 0 | 0
0 |  |  | 0 | 0
0 |  |  | 0 | 0
Note on A4: +annette.dougherty@noaa.gov Hi Annette, can you verify that I copied these totals over correctly (Column J-P) from your cruise summary. please also double check if anything prior to that is incorrect (column A-I). Thanks! -heather _Assigned to Annette Dougherty - NOAA Federal_ -Heather Tabisola - NOAA Affiliate
Note on L3: +peter.proctor@noaa.gov Welcome back Peter! I am in need of Cruise Plans, Reports, Logs and details here, ASAP. PLEASE :) _Assigned to Peter Proctor - NOAA Affiliate_ -Heather Tabisola - NOAA Affiliate
Note on L6: +rmccabe.ocean@gmail.com Ryan, I need these stats filled out as soon as your back please. I need them for the review. _Assigned to Ryan McCabe_ -Heather Tabisola - NOAA Affiliate
Note on L12: +peter.proctor@noaa.gov Fall Mooring cruise stats here please. _Assigned to Peter Proctor - NOAA Affiliate_ -Heather Tabisola - NOAA Affiliate

## Sheet8
DAS | Cruise Location | Name: Activities | Project | Project
2 | Puget Sound | / Gear Trials (OMAO-5410): Equipment: TBD; ITAE Technologies: None; DBO: No | n/a | MACE
14 | Bering Sea | Spring Mooring/ FOCI Moorings - Bering Sea (DY19-04): Equipment: Moorings (w/ Prawler), CTD, bongo, CalVet, towfish; ITAE Technologies: Oculus (401 deploy, 40X back-up); DBO: No | EcoFOCI | NPCREP, EcoFOCI | EcoFOCI | 169
21 | Gulf of Alaska | WGOA Ichthyoplankton/ EMA-FOCI Larval Groundfish Assessment (DY19-05): Equipment: neuston, bongo, fastcat, CalVET, drifters; ITAE Technologies: None; DBO: No | EcoFOCI | NPCREP, EcoFOCI, EMA
35 | Gulf of Alaska | GOAOA/ Gulf of Alaska Ocean Acidification (Cancelled): Equipment: CTD, bongo; ITAE Technologies: None; DBO: No | OAP | OAP
25 | US Arctic: Chukchi Sea | Arctic Integrated Ecosystem Survey: MOORINGS Leg 1/ NPRB Arctic IERP (OS19-01): Equipment: acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (401 recover & 404 deploy), Pop-up (4), RAS mooring (1), SM Prawler (TBD); DBO: Yes | EcoFOCI | NPRB AIERP
22 | US Arctic: Chukchi Sea | DBO-NCIS Moorings/ NOAA Arctic Distributed Biological Observatories-Northern Chuckchi Integrated Studies (DBO-NCIS) (HL19-00): Equipment: CTD, bongo; ITAE Technologies: TBD; DBO: Yes | EcoFOCI | EcoFOCI & ITAE
14 | Gulf of Alaska | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 1): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EcoFOCI | EMA, EcoFOCI
21 | US Arctic: Chukchi Sea | Arctic Integrated Ecosystem Survey: TRAWLING Leg 2/ NPRB Arctic IERP (OS-19-02): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: None; DBO: Yes | EcoFOCI | NPRB AIERP
17 | Gulf of Alaska | YOY Pollock/ EMA/FOCI Age-0 Groundfish and Salmon Recruitment Processes (DY19-07 Leg 2): Equipment: midwater trawl, CTD, bongo; ITAE Technologies: None; DBO: No | EcoFOCI | EMA, EcoFOCI
20 | US Arctic: Chukchi Sea | Arctic Integrated Ecosystem Survey: TRAWLING Leg 3/ NPRB Arctic IERP (OS19-03): Equipment: surface trawl, beam trawl, acoustics, CTD, bongo, towfish, moorings; ITAE Technologies: Oculus (404 recover), Pop-up (TBD); DBO: Yes | EcoFOCI | NPRB AIERP
15 | Bering Sea | Fall Mooring/ FOCI Moorings - Bering Sea (DY19-08): Equipment: Moorings, CTD, bongo, CalVet; ITAE Technologies: Oculus (B recover), Pop-up (TBD); DBO: Yes | EcoFOCI | EMA, EcoFOCI
| Gulf of Alaska | EGOA SECM Survey/ Eastern Gulf of Alaska(EGOA) Southeast Alaska Coastal Monitoring (SECM) Survey (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | n/a | EMA
| US Arctic: Bering Sea | EMA/ADFG NBS/ Joint AFSC/ADFG research/ EMA/ADFG NBS/ Joint AFSC/ADFG research (XX19-00): Equipment: surface trawl, CTD, bongo; ITAE Technologies: None; DBO: No | n/a | EMA
21 | US Arctic: Bering Sea | Eastern Bering Sea Bottom Trawl Survey Leg 3/ Eastern Bering Sea Bottom Trawl Survey (AK19-01): Equipment: moorings; ITAE Technologies: None; DBO: No | n/a | MACE

## OPERATION TIMELINE B (hidden)
Cruise No. | Ship | Cruise Dates | Port of Dep/Arriv | Drop-dead Date | Shipment Details | Moorings Deployed | Vehicles deployed | FOCI Lead | Hazmats
DY19-04 | Oscar Dyson | 4/19-5/02 | Kodiak/Dutch | 2019-04-05 | Load at pier 91, 8th and 9th of April | 19CB1A, 19BSM2A, 19BSP2A, 19BSITAEPR-2A | 401 Oculus deployed | Lebon/Grassia | Y
MML, AL19_AU_BS4, AL19_AU_BS6, AL19_AU_BS3
|  |  |  | 2019-06-02 | Return Shipment June 2nd from Kodiak by barge following DY19-03 |  |  |  | Y
OS19-01 | Ocean Starr | 8/01-8/24 | Dutch/Nome |  | Load Seattle, early July, at Stabbert Maritime dock | 19CKIP1A, 19CKP1A, 19CKIP2A, 19CKP2A, 19CKIP3A | 404, 4XX Oculus deployed | Lebon/Grassia | Y
[6 empty] | 19CKP3A, 19CKP4A, 19CKP5A, 19CKP12A | 401 Oculus recovered
19CKR2A, 19CKR2B, 19CKITAEPR2A
Pop-ups: 201, 202, 203, 204
Plus UAF moorings
MML, AL19_AU_NM1, AL19_AU_BF2, AL19_AU_PH1
AL19_AU_CL1, AL19_AU_IC1, AL19_AU_IC2, AL19_AU_IC3
AL19_AU_PB1, AL19_AU_WT1
OS19-02 | Ocean Starr | 8/25-9/12 | Nome/Nome |  | Load Fisheries Doors, and other equipment |  |  | Donohoe | N
OS19-03 | Ocean Starr | 9/13-10/04 | Nome/Dutch |  |  | MML, AL19_AU_BS2 | 404 Oculus recovered | Strausz | N/A
Pop-ups: 208, 209, 210, 211, 212
Return Shipment Starr to Seattle?
DY19-08 | Oscar Dyson | 9/18-10/08? | Dutch/Kodiak |  | Ship early Sept | 19BS2C, 19BSP2B, 19BS4B, 19BSP4A | 4XX Oculus recovered | Lebon | Y
19BS5A, 19BSP5A, 19BS8A, 19BSP8A, 19CB1B
Plus MML, AL19_AU_BS1, AL19_AU_BS3??
Pop-ups: 205, 206, 207, 213, 214, 215, 216, 217, 218, 219, 220, 221, 222, 223
Return Shipment on Dyson to lower 48
TBD | Pacific Knight |  | Dutch/Dutch |  | June? | 75 kHz ADCP, 300 kHz ADCP | none | Lebon | N