## KA 155,170 Jun01 Mod2
NOAA SHIP KA'IMIMOANA
KA-03-06 (16 OCT - 14 NOV 2003)
TAO: GP7-03-KA
| Activity |  | Latitude |  | Longitude |  |  | Deployed | Dist. | Speed | Transit | On Sta | Arrive | Depart | Cumulative |  |  |  |  | SWAP | DEPLOY | LAT | LONG
|  | Deg. | Min |  | Deg. | Min. |  | (mos) | (nmi) | (kts) | (hrs) | (hrs) | Date / Time | Date / Time | (hrs) | (days) | RECOVER | VISIT | REPAIR | OUT | ONLY | CORR | CORR |  |  |  |  | AT SITE | LAST RECOV | DIFFERENCE
| HONOLULU | 21 | 18 | N | 157 | 53 | W | [6 empty] | 2003-10-16 14:00 | 0 | 0 | [5 empty] | 1 | 1 | 21 | N | 157 | 0 | 0 |  | 0
| CTD | 12 | 0 | N | 155 | 0 | W |  | 582.03 | 10 | 58.203 | 1.2 | 2003-10-19 00:12 | 2003-10-19 01:24 | 59.403 | 2.4751 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 | N | 155 | 0 | 0 |  | 0 | 5820.2998
| CTD | 11 | 0 | N | 155 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-10-19 07:24 | 2003-10-19 08:36 | 66.603 | 2.7751 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11 | N | 155 | 0 | 0 |  | 0 | 600
| CTD | 10 | 0 | N | 155 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-10-19 14:36 | 2003-10-19 15:48 | 73.803 | 3.0751 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 10 | N | 155 | 0 | 0 |  | 0 | 600
| CTD | 9 | 0 | N | 155 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-10-19 21:48 | 2003-10-19 23:00 | 81.003 | 3.3751 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9 | N | 155 | 0 | 0 |  | 0 | 600
R E | EPAIR TAUT-NG, & CTD, SWAP ATRH | 8 | 0 | N | 155 | 0 | W | 28.4986 | 60 | 10 | 6 | 8 | 2003-10-20 05:00 | 2003-10-20 13:00 | 95.003 | 3.9585 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 8 | N | 155 | 0 | 37914.2085 | 2001-06-03 | 28.4986 | 600
| CTD | 7 | 0 | N | 155 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-10-20 19:00 | 2003-10-20 20:12 | 102.203 | 4.2585 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7 | N | 155 | 0 | 0 |  | 0 | 600
| CTD | 6 | 0 | N | 155 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-10-21 02:12 | 2003-10-21 03:24 | 109.403 | 4.5585 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 6 | N | 155 | 0 | 0 |  | 0 | 600
R | ECOVER/DEPLOY, CTD | 5 | 0 | N | 155 | 0 | W | 28.5046 | 60 | 10 | 6 | 12 | 2003-10-21 09:24 | 2003-10-21 21:24 | 127.403 | 5.3085 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 5 | N | 155 | R | 37915.3918 | 2001-06-04 | 28.5046 | 600
| CTD | 4 | 0 | N | 155 | 0 | W |  | 60 | 10 | 5.9 | 1.2 | 2003-10-22 03:18 | 2003-10-22 04:30 | 134.503 | 5.6043 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | N | 155 | 0 | 0 |  | 0 | 600
| CTD | 3 | 0 | N | 155 | 0 | W |  | 60 | 10 | 5.9 | 1.2 | 2003-10-22 10:24 | 2003-10-22 11:36 | 141.603 | 5.9001 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | N | 155 | 0 | 0 |  | 0 | 600
| CTD | 2 | 30 | N | 155 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-10-22 14:36 | 2003-10-22 15:48 | 145.803 | 6.0751 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | N | 155 | 0 | 0 |  | 0 | 300
V | ISIT (INSERT/FAIRED) & CTD | 2 | 0 | N | 155 | 0 | W | 28.4847 | 30 | 10 | 3 | 2 | 2003-10-22 18:48 | 2003-10-22 20:48 | 150.803 | 6.2835 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | N | 155 | V | 37916.7835 | 2001-06-06 | 28.4847 | 300
| CTD | 1 | 30 | N | 155 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-10-22 23:48 | 2003-10-23 01:00 | 155.003 | 6.4585 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | N | 155 | 0 | 0 |  | 0 | 300
| CTD | 1 | 0 | N | 155 | 0 | W |  | 30 | 10 | 3.2 | 1.2 | 2003-10-23 04:12 | 2003-10-23 05:24 | 159.403 | 6.6418 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | N | 155 | 0 | 0 |  | 0 | 300
| CTD | 0 | 30 | N | 155 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-10-23 08:24 | 2003-10-23 09:36 | 163.603 | 6.8168 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | N | 155 | 0 | 0 |  | 0 | 300
R | ECOVER/DEPLOY MBARI TAUT-NG (INSERT/FAIRED) & CTD | 0 | 0 |  | 155 | 0 | W | 24.5418 | 30 | 10 | 3 | 14 | 2003-10-23 12:36 | 2003-10-24 02:36 | 180.603 | 7.5251 | 1 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 155 | R | 37917.5251 | 2001-10-05 | 24.5418 | 300
| CTD | 0 | 30 | S | 155 | 0 | W |  | 30 | 10 | 3.3 | 1.2 | 2003-10-24 05:54 | 2003-10-24 07:06 | 185.103 | 7.7126 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | S | 155 | 0 | 0 |  | 0 | 300
| CTD | 1 | 0 | S | 155 | 0 | W |  | 30 | 10 | 2.8 | 1.2 | 2003-10-24 09:54 | 2003-10-24 11:06 | 189.103 | 7.8793 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 1 | S | 155 | 0 | 0 |  | 0 | 300
| CTD | 1 | 30 | S | 155 | 0 | W |  | 30 | 10 | 2.7 | 1.2 | 2003-10-24 13:48 | 2003-10-24 15:00 | 193.003 | 8.0418 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 1 | S | 155 | 0 | 0 |  | 0 | 300
R E | ECOVER/DEPLOY TAUT-NG & CTD, SST w/ picklefork | 2 | 0 | S | 155 | 0 | W | 24.5492 | 30 | 10 | 3 | 22 | 2003-10-24 18:00 | 2003-10-25 16:00 | 218.003 | 9.0835 | 0 | 0 | 1 | 0 | 0 | -1 | 1 | 2 | S | 155 | 0 | 37918.7501 | 2001-10-06 | 24.5492 | 300
| CTD | 2 | 30 | S | 155 | 0 | W |  | 30 | 10 | 2.8 | 1.2 | 2003-10-25 18:48 | 2003-10-25 20:00 | 222.003 | 9.2501 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 2 | S | 155 | 0 | 0 |  | 0 | 300
| CTD | 3 | 0 | S | 155 | 0 | W |  | 30 | 10 | 2.7 | 1.2 | 2003-10-25 22:42 | 2003-10-25 23:54 | 225.903 | 9.4126 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 3 | S | 155 | 0 | 0 |  | 0 | 300
| CTD | 4 | 0 | S | 155 | 0 | W |  | 60 | 10 | 5.7 | 1.2 | 2003-10-26 05:36 | 2003-10-26 06:48 | 232.803 | 9.7001 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 4 | S | 155 | 0 | 0 |  | 0 | 600
R | ECOVER/DEPLOY TAUT-NG & CTD | 5 | 0 | S | 155 | 0 | W | 24.5743 | 60 | 10 | 5.6 | 12 | 2003-10-26 12:24 | 2003-10-27 00:24 | 250.403 | 10.4335 | 1 | 0 | 0 | 0 | 0 | -1 | 1 | 5 | S | 155 | R | 37920.5168 | 2001-10-07 | 24.5743 | 600
| CTD | 6 | 0 | S | 155 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-10-27 06:24 | 2003-10-27 07:36 | 257.603 | 10.7335 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 6 | S | 155 | 0 | 0 |  | 0 | 600
| CTD | 7 | 0 | S | 155 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-10-27 13:36 | 2003-10-27 14:48 | 264.803 | 11.0335 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 7 | S | 155 | 0 | 0 |  | 0 | 600
V | ISIT TAUT-NG & CTD | 8 | 0 | S | 155 | 0 | W | 24.553 | 60 | 10 | 6 | 2 | 2003-10-27 20:48 | 2003-10-27 22:48 | 272.803 | 11.3668 | 0 | 1 | 0 | 0 | 0 | -1 | 1 | 8 | S | 155 | V | 37921.8668 | 2001-10-09 | 24.553 | 600
R | ECOVER/DEPLOY TAUT-NG & CTD | 8 | 0 | S | 170 | 0 | W | 24.5463 | 891.1916 | 10 | 89.1192 | 12 | 2003-10-31 15:55 | 2003-11-01 03:55 | 373.9222 | 15.5801 | 1 | 0 | 0 | 0 | 0 | -1 | 1 | 8 | S | 170 | R | 37925.6634 | 2001-10-13 | 24.5463 | 8911.9163
| CTD | 7 | 0 | S | 170 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-11-01 09:55 | 2003-11-01 11:07 | 381.1222 | 15.8801 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 7 | S | 170 | 0 | 0 |  | 0 | 600
| CTD | 6 | 0 | S | 170 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-11-01 17:07 | 2003-11-01 18:19 | 388.3222 | 16.1801 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 6 | S | 170 | 0 | 0 |  | 0 | 600
V | ISIT TAUT-NG & CTD | 5 | 0 | S | 170 | 0 | W | 28.4922 | 60 | 10 | 6 | 2 | 2003-11-02 00:19 | 2003-11-02 02:19 | 396.3222 | 16.5134 | 0 | 1 | 0 | 0 | 0 | -1 | 1 | 5 | S | 170 | V | 37927.0134 | 2001-06-16 | 28.4922 | 600
| CTD | 4 | 0 | S | 170 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-11-02 08:19 | 2003-11-02 09:31 | 403.5222 | 16.8134 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 4 | S | 170 | 0 | 0 |  | 0 | 600
| CTD | 3 | 0 | S | 170 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-11-02 15:31 | 2003-11-02 16:43 | 410.7222 | 17.1134 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 3 | S | 170 | 0 | 0 |  | 0 | 600
| CTD | 2 | 30 | S | 170 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-11-02 19:43 | 2003-11-02 20:55 | 414.9222 | 17.2884 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 2 | S | 170 | 0 | 0 |  |  | 300
V | ISIT MBARI - TAUT-NG & CTD | 2 | 0 | S | 170 | 0 | W | 24.5573 | 30 | 10 | 3 | 12 | 2003-11-02 23:55 | 2003-11-03 11:55 | 429.9222 | 17.9134 | 0 | 1 | 0 | 0 | 0 | -1 | 1 | 2 | S | 170 | V | 37927.9968 | 2001-10-15 | 24.5573 | 300
| CTD | 1 | 30 |  | 170 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-11-03 14:55 | 2003-11-03 16:07 | 434.1222 | 18.0884 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 1 | 0 | 170 | 0 | 0 |  | 0 | 300
| CTD | 1 | 0 | S | 170 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-11-03 19:07 | 2003-11-03 20:19 | 438.3222 | 18.2634 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 1 | S | 170 | 0 | 0 |  | 0 | 300
| CTD | 0 | 30 | S | 170 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-11-03 23:19 | 2003-11-04 00:31 | 442.5222 | 18.4384 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | S | 170 | 0 | 0 |  |  | 300
R E | EPAIR TAUT-NG (FAIRINGS & SONTEK. NOTE: NO INSERT) & CTD, SWAP AN | 0 | 0 |  | 170 | 0 | W | 28.4966 | 30 | 10 | 3 | 10 | 2003-11-04 03:31 | 2003-11-04 13:31 | 455.5222 | 18.9801 | 0 | 0 | 1 | 0 | 0 | -1 | 1 | 0 | 0 | 170 | 0 | 37929.1468 | 2001-06-18 | 28.4966 | 300
| AVOID SS ADCP | 0 | 0 |  | 170 | 0 | W |  | 0 | 10 | 0 | 0 | 2003-11-04 13:31 | 2003-11-04 13:31 | 455.5222 | 18.9801 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 170 | 0 | 0 | 2001-06-18 | -1215.082 | 0
| CTD | 0 | 30 | N | 170 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-11-04 16:31 | 2003-11-04 17:43 | 459.7222 | 19.1551 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | N | 170 | 0 | 0 |  |  | 300
| CTD | 1 | 0 | N | 170 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-11-04 20:43 | 2003-11-04 21:55 | 463.9222 | 19.3301 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | N | 170 | 0 | 0 |  | 0 | 300
| CTD | 1 | 30 | N | 170 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-11-05 00:55 | 2003-11-05 02:07 | 468.1222 | 19.5051 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | N | 170 | 0 | 0 |  |  | 300
R | /D TAUT-NG (FAIRED, NOTE: NO INSERT) & CTD | 2 | 0 | N | 170 | 0 | W | 94.8595 | 30 | 10 | 3 | 16 | 2003-11-05 05:07 | 2003-11-05 21:07 | 487.1222 | 20.2968 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | N | 170 | R | 37930.2134 | 1995-12-04 | 94.8595 | 300
| CTD | 2 | 30 | N | 170 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-11-06 00:07 | 2003-11-06 01:19 | 491.3222 | 20.4718 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | N | 170 | 0 | 0 |  |  | 300
| CTD | 3 | 0 | N | 170 | 0 | W |  | 30 | 10 | 3 | 1.2 | 2003-11-06 04:19 | 2003-11-06 05:31 | 495.5222 | 20.6468 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | N | 170 | 0 | 0 |  | 0 | 300
| CTD | 4 | 0 | N | 170 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-11-06 11:31 | 2003-11-06 12:43 | 502.7222 | 20.9468 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | N | 170 | 0 | 0 |  | 0 | 600
R E | EPAIR TAUT-NG & CTD, SWAP ANEMOMETER | 5 | 0 | N | 170 | 0 | W | 28.4846 | 60 | 10 | 6 | 6 | 2003-11-06 18:43 | 2003-11-07 00:43 | 514.7222 | 21.4468 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 5 | N | 170 | 0 | 37931.7801 | 2001-06-21 | 28.4846 | 600
| CTD | 6 | 0 | N | 170 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-11-07 06:43 | 2003-11-07 07:55 | 521.9222 | 21.7468 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 6 | N | 170 | 0 | 0 |  | 0 | 600
| CTD | 7 | 0 | N | 170 | 0 | W |  | 60 | 10 | 6 | 1.2 | 2003-11-07 13:55 | 2003-11-07 15:07 | 529.1222 | 22.0468 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7 | N | 170 | 0 | 0 |  | 0 | 600
R | ECOVER/DEPLOY ATLAS II & CTD | 8 | 0 | N | 170 | 0 | W | 24.5862 | 60 | 10 | 6 | 24 | 2003-11-07 21:07 | 2003-11-08 21:07 | 559.1222 | 23.2968 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 8 | N | 170 | R | 37932.8801 | 2001-10-19 | 24.5862 | 600
R E | EPAIR TAUT-NG & CTD, INSTALL SST W/ PICKLEFORK | 8 | 0 | N | 180 | 0 | W | 23.7494 | 594.1462 | 10 | 59.4146 | 6 | 2003-11-11 08:32 | 2003-11-11 14:32 | 624.5368 | 26.0224 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 8 | N | 180 | 0 | 37936.3557 | 2001-11-17 | 23.7494 | 5941.4619
| KWAJALEIN | 8 | 43 | N | 167 | 44 | E |  | 729.4164 | 10 | 72.9416 |  | 2003-11-14 15:29 |  | 697.4784 | 29.0616 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 8 | N | 167 | 0 | 0 |  | 0 | 7294.1641
[9 empty] | 4956.7842 |  | 418.0754 | 198.4 |  |  |  |  | 6 | 4 | 5 | 0 | 0 | [9 empty] | 10
~ DAYS AT SEA ~
[5 empty] | 155W LINE = |  | 7.7417 | Days |  |  |  | Hono - 8N/155W = |  | 762.03 |  |  | 37939 | 37910
[5 empty] | 170W LINE = |  | 8.2167 | Days |  |  |  | 155W - 170W = |  | 2871.1916
| RECOVER TAUTLINE NEXT GEN = | 6 |  |  | TRANSIT = |  | #REF! | Days |  |  |  | 8N/170W - Kwaj = |  | 1323.5626
| DEPLOY TAUTLINE NEXT GEN = | 7 |  |  | TOTALS = |  | #REF! | Days |  |  |  | Total Distance = |  | 4956.7842
| RECOVER / DEPLOY SUBSURFACE ADCP = | 0 |  |  | ** ALL TIMES ARE HAWAIIAN STANDARD TIME (HST) ** | [6 empty] | ** NOT ADJUSTED FOR DATELINE CROSSING **
| VISITS STD ATLAS (2) & TAUT-NG (2) = | 4
| DEPLOY SOLO DRIFTER BUOYS = | 12
Formulas:
Arrive = [Depart, row above]+[Transit]/24
Arrive = O34+[Transit]/24
Depart = [Arrive]+[On Sta]/24